THE 1140-A COMPANY Cape Cod Comedy Traditional Media PR Playbook A launch-day checklist, press-pack specification, story-hook bank, reviewer strategy, and over-inclusive media directory for Cape Cod and Massachusetts Prepared in British English ¦ Routes checked against public sources ¦ 12 July 2026

What this document is - and is not • It is a working playbook and selection list, deliberately broader than a normal first-wave media list. • It does not draft the press release. It specifies every component needed to make the eventual release, pitch, listing and advisory easy to publish. • It assumes the first event will be a one-day Cape Cod comedy event in a venue of at least 300 seats, with the venue, date, ticket link and talent still to be confirmed. • It uses the name "The 1140-A Company" as supplied. Lock the legal and public-facing styling before launch.

Internal working document - update contacts and deadlines immediately before each campaign

# Contents and working method

| Section | Purpose |
| --- | --- |
| 1 | Launch strategy at a glance |
| 2 | Positioning, language and publishable hooks |
| 3 | The master private press package |
| 4 | The safe public website media package |
| 5 | What each media type expects |
| 6 | Email, follow-up and launch sequence |
| 7 | Reviewer, critic and complimentary-ticket plan |
| 8 | Day-of media operations and post-event proof |
| 9 | Prioritised Cape Cod and Massachusetts media directory |
| 10 | Long-shot national and trade targets |
| 11 | Launch-day, fact-check and tracking checklists |
| 12 | Source, verification and maintenance notes |

How to use the directory • A = send personally in the first wave. B = strong second wave or dependent on venue/talent geography. C = legitimate long shot. D = one-in-a-million, tie-dependent or legacy route that must be re-verified. $ = paid distribution or listing rather than earned editorial coverage. • V in the text means the route was visible on an official public page when checked. H means use the official homepage/contact page and confirm the current desk. D means the outlet was identified through a current media directory and should be re-checked. • When the venue is confirmed, promote that town's newspaper, chamber, community television service, cultural council and municipal calendar to A priority, regardless of its present ranking. • Do not send one identical email to every row. Use the pack code and the outlet-specific angle in the table.

The practical rule: build once, publish many ways.

Create one definitive fact base, one rights-cleared asset library and one stable media-kit URL. Then produce short, medium and long text versions so an editor can paste the correct version without rewriting facts or chasing assets.

# 1. Launch strategy at a glance

## The recommended order of attack

| Step | Action | What it means |
| --- | --- | --- |
| 1 | Pre-build everything before confirmation | Prepare templates, legal wording, photo specifications, founder biography, organisation facts, media list, website press area and tracking sheet. Leave only date, venue, line-up, ticket link and final quotes blank. |
| 2 | Confirm and freeze the facts | Obtain written approval of every talent name, billing order, biography, credit, image, venue detail, age guidance, ticket price, accessibility statement and quote. Do not announce on a handshake. |
| 3 | Personal first wave | Send the venue-town weekly/local paper, Cape Cod Times, CAI, CapeCod.com/CCB, the relevant Cape newspaper, ArtsCapeCod, town calendar and the most suitable Boston feature targets. Personalise the first two paragraphs. |
| 4 | Structured listing wave | Submit calendar forms separately using the exact fields requested. Do not assume a newsroom email also feeds the outlet calendar. |
| 5 | Broadcast wave | Send public-service/community-calendar copy to eligible radio and community television outlets; send a visual feature pitch and b-roll link to television assignment desks. |
| 6 | Statewide and long-tail wave | Use the Massachusetts regional list, identity/community outlets only where there is an authentic tie, and paid NENPA distribution only after the core personal pitches are sent. |
| 7 | Follow-up and proof | One polite follow-up, a 72-hour media advisory, then a post-event package with attendance, photography, audience reaction and the next concrete milestone. |

## The one-sentence strategic position

Internal positioning line - not final release copy • A Cape-based non-profit organisation is building a durable live-comedy tradition for residents and visitors by curating accomplished and breakout-ready comedians, treating artists professionally and giving Cape audiences a high-quality night close to home. • Externally, do not say "the comic first and the audience second". That can sound as though patrons are secondary. Translate the principle into two positive commitments: artist-respect and audience-quality.

## What success looks like for the first event

[ ] Every calendar listing carries identical date, time, venue, ticket, age and accessibility facts.

[ ] At least one Cape-wide editorial preview and one venue-town/local preview are published.

[ ] At least one radio or television segment, community notice, ticket giveaway or presenter mention is secured.

[ ] At least three credible reviewers, arts writers or local journalists receive an invitation with no expectation of favourable coverage.

[ ] The public media kit remains live after the event and becomes proof for the second event.

[ ] The post-event file includes attendance, photographs, accurate quotes, press links and a concise "what comes next".

## Facts that must be locked before sending

| Organisation identity | Exact legal name, public brand, non-profit status, Massachusetts registration, tax-exempt status if any, and approved one-sentence mission. |
| --- | --- |
| Event identity | Final event title, date, doors, show time, interval, estimated finish, one-day/one-night wording, and whether this is the inaugural event. |
| Venue | Legal venue name, street address, town, seating capacity actually configured for the show, parking/transit, accessibility and press check-in location. |
| Tickets | Live public URL, prices including fees, on-sale time, refund policy, age guidance, group or community allocation, and box-office contact. |
| Talent | Billing order, exact spelling, pronouns, hometown/current base, approved credits, short/medium biographies, approved photographs, quote approval and interview availability. |
| Content guidance | Accurate description such as "adult comedy with risqué material but not built around constant profanity"; never call it family-friendly or clean unless the complete set supports that claim. |
| Spokespeople | Primary spokesperson, backup, written-Q&A option, interview windows, phonetic pronunciation, mobile contact for producers only. |
| Rights | Photo, video, logo, music and clip permissions in writing; mandatory credit lines; expiry or territory limits. |
| Claims | Proof for "first", "only", "non-profit", "300+ seats", historical statements, charitable benefit, community impact and every superlative. |
| Emergency changes | Single source of truth, approval chain, cancellation/postponement wording and immediate correction procedure. |

# 2. Positioning, language and publishable hooks

## The strongest hook hierarchy

| Rank | Hook | How to make it publishable |
| --- | --- | --- |
| 1 | Giving Cape Cod a durable comedy institution | Lead with the benefit to the Cape, not dissatisfaction with what exists. The organisation is investing in a recurring cultural experience for residents and visitors. |
| 2 | Reviving a Cape entertainment tradition | Use positive continuity: the Cape has a remembered history as a destination for major live entertainment, and this project adds a contemporary comedy chapter. Support the claim with archive evidence. |
| 3 | A non-profit, mission-led model | Explain precisely what the legal structure changes: reinvestment, artist treatment, community access, programming quality or long-term cultural infrastructure. "Non-profit" alone is not the story. |
| 4 | See the next wave before the wider breakthrough | Curate comedians with verifiable momentum: television credits, festival selections, respected club residencies, podcast audiences, writing credits, awards or recent sell-outs. |
| 5 | A Cape resident building for the place where they live | "Resident giving to the Cape" is credible and warm. Use "Cape resident", not "Cape native" or "from Cape Cod", unless true. |
| 6 | Artist respect produces a better audience experience | Translate "comic first" into practical standards: fair treatment, thoughtful billing, sensible travel, good sound, proper green-room support and a room designed for comedy. |
| 7 | A grown-up night out without wall-to-wall profanity | Use only after reviewing all sets. "Risqué, smart adult comedy" is safer than "clean". Be candid about age and content guidance. |
| 8 | A 300-plus-seat, one-day cultural event | Scale and scarcity can make the first event newsworthy. Use actual configured capacity, not the venue's theoretical maximum. |
| 9 | Residents and summer visitors in the same room | A Cape-specific audience story: an event designed for year-round Cape Codders as well as visitors, without suggesting either group is an afterthought. |
| 10 | A local cultural and night-time-economy contribution | Use only with evidence: local venue spend, lodging, dining partnerships, local staffing or off-season scheduling. Avoid unsupported economic-impact numbers. |
| 11 | A founding night, not a disposable pop-up | Show the wider plan without overpromising dates: the first proof point in a mission to re-establish the Cape as a meaningful stop for exceptional comedy. |
| 12 | Talent-specific hooks | The most publishable hook may be the headliner's current project, Massachusetts connection, Cape memory, unusual career route, public-service work or imminent release. Build one tailored pitch per comic. |

## Historical proof pack for the "return to the comedy route" angle

[ ] Two or three dated Cape Cod newspaper clippings, venue adverts, programmes or posters showing notable comedy bookings in the 1980s or another clearly defined period.

[ ] Accurate venue names and dates, including but not limited to the Melody Tent; avoid saying "all the arenas" without examples.

[ ] One short founder memory labelled as personal recollection, not presented as the sole historical evidence.

[ ] A short quote from a local venue operator, historian, long-time resident or arts figure, independently approved.

[ ] A neutral line acknowledging the Cape's current comedy and arts scene. The project is adding capacity and ambition, not declaring that nothing exists.

[ ] Source notes for every archive image. Do not place copyrighted clippings in the public kit without permission; use them as research or link to the archive.

## Language guardrails: use this, avoid that

| Use | Avoid |
| --- | --- |
| "The 1140-A Company is a Massachusetts non-profit organisation..." | "Charity", "501(c)(3)" or "tax-deductible" unless each claim is confirmed and approved. |
| "A Cape resident creating a new live-comedy tradition..." | "Cape native", "born and raised here" or "from the Cape" unless true. |
| "Rekindling a remembered Cape tradition of destination entertainment..." | "Bringing comedy back because the Cape has nothing now." |
| "Artist-respect and audience-quality are the operating principles." | "The comic comes first and the audience second." |
| "Accomplished and breakout-ready comedians, with credits including..." | "Top comics", "the best comedians" or "future stars" without objective proof. |
| "Adult comedy with risqué material and limited reliance on profanity" | "Clean", "wholesome" or "family-friendly" unless every performer and set truly fits. |
| "Inaugural event" or "first event produced by The 1140-A Company" | "Cape Cod's first..." or "the only..." unless a documented search supports it. |
| "One-night showcase" | "One night only" if a second performance may be added. |
| "Ticket prices are..." and "a portion supports..." with exact figures | Vague charitable-benefit wording or implying the full ticket price is a donation. |
| "Configured for approximately [X] seats for this event" | The building's maximum capacity if the event layout is smaller. |

## Claim substantiation register

Maintain this table internally. A publish-ready package is only as reliable as the evidence behind its most attractive claims.

| Proposed claim | Evidence held | Approved wording | Owner / approval | Expiry or re-check |
| --- | --- | --- | --- | --- |
| Non-profit status | [insert filings/status] | [insert precise legal wording] | [name] | [date] |
| Tax-exempt / charitable status | [insert IRS/MA evidence or "not claimed"] | [approved wording] | [counsel/accountant] | [date] |
| Cape entertainment-history claim | [archive links/clippings] | [approved neutral line] | [research owner] | [date] |
| Venue capacity | [contract / floor plan] | [configured capacity] | [venue] | [event date] |
| Talent credit or audience metric | [official biography/source] | [exact credit] | [talent manager] | [date checked] |
| Community/economic benefit | [partner data/budget] | [measured wording only] | [organisation] | [post-event] |

Legal-status caution • "Non-profit corporation", "tax-exempt organisation", "public charity" and "registered charitable organisation" are not interchangeable descriptions. • Do not state or imply that ticket purchases or sponsorships are tax-deductible unless the organisation's adviser has approved the exact wording and any required value disclosure. • Massachusetts charitable-solicitation and registration rules may apply separately from incorporation or federal tax status. Confirm before fundraising language is used. • This playbook is operational guidance, not legal or tax advice.

# 3. The master private press package

Build a complete private master folder, then send only the subset needed by each outlet. The master is the source of truth; the public website kit is a stripped, rights-cleared mirror.

## Master folder structure

| Folder | Contents |
| --- | --- |
| 00_READ-ME | Version number, last-updated date, approved contact, event status, rights notes and a one-page asset index. |
| 01_FACT-BASE | Locked event fact sheet, organisation fact sheet, claim register, ticket facts, venue facts, accessibility, age/content guidance and pronunciation guide. |
| 02_RELEASES-AND-ADVISORIES | Final press release in DOCX, PDF and plain text; 72-hour media advisory; day-of visual advisory; post-event results note. This playbook does not draft those items. |
| 03_COPY-BANK | 25-, 50-, 100-, 150-, 250- and 400-word descriptions; 15-, 30- and 60-second radio copy; social captions; calendar fields; headline and subject-line bank. |
| 04_ORGANISATION | Approved short/medium founder biography, organisation boilerplate, mission, governance facts suitable for media, high-resolution logo files and brand spelling. |
| 05_TALENT | One folder per performer: approved billing name, 50/100/200-word biographies, credits, links, headshots, captions, interview availability, pronunciation, content notes and manager approval. |
| 06_PHOTOGRAPHY | Hero landscape, portrait, square, venue exterior/interior, founder/spokesperson, line-up composite only if rights permit, captions, credits and licence/usage note. |
| 07_VIDEO-AND-B-ROLL | Horizontal and vertical b-roll, clean short performance clips, venue shots, founder/talent sound bites, transcript, shot list, music-rights note and download links. |
| 08_AUDIO | 15/30/60-second announcer copy, clean WAV/MP3 clips, pronunciations, short radio-ready answers and a no-music version. |
| 09_MEDIA-OPERATIONS | Press invitation, credential form, comp-ticket policy, press holds, seating map, photo policy, arrival time, parking, on-site contact and interview schedule. |
| 10_TRACKING-AND-PROOF | Contact log, submitted-calendar log, coverage links/PDFs, screenshots, reviewer attendance, corrections, attendance, audience feedback, approved post-event photographs and next-event proof. |

## The publish-ready text inventory

[ ] Master press release: inverted-pyramid structure, factual headline/subheading, Cape dateline, 5Ws in the opening, two approved quotes, talent proof, organisation boilerplate, media contact and ticket link.

[ ] Media advisory: one page, highly scannable, labelled WHAT / WHO / WHEN / WHERE / WHY / VISUALS / INTERVIEWS / PRESS CONTACT.

[ ] 25-word listing: event name, leading talent, date, town, ticket URL.

[ ] 50-word listing: add concise mission and content/age guidance.

[ ] 100-word listing: add talent credits and one Cape hook.

[ ] 150-word listing: most useful for community calendars, radio diaries and newsletters.

[ ] 250-word ready-to-run brief: local newspapers and community media can publish it with minimal editing.

[ ] 400-word release body: enough context for an editor, but still concise; any longer background goes in the fact sheet.

[ ] Founder biography in 50, 100 and 200 words; avoid autobiography in the release.

[ ] Talent biographies in 50, 100 and 200 words with only current, approved credits.

[ ] Organisation boilerplate in 60-90 words, including exact legal/non-profit language.

[ ] Quote bank: founder, venue, community/arts partner and each key comic; every quote should add a fact, point of view or human line rather than praise the event generically.

## Fact sheet fields

[ ] Event title and one-sentence description

[ ] Date and day of week

[ ] Doors, start, interval and finish

[ ] Venue legal/public name

[ ] Street address and Cape town

[ ] Configured capacity

[ ] Ticket prices and fees

[ ] On-sale date/time

[ ] Ticket URL and box office

[ ] Age recommendation / admission rule

[ ] Accessibility and accommodation contact

[ ] Parking/public transport

[ ] Full billing order

[ ] Approved talent credits

[ ] Content guidance

[ ] Running order policy

[ ] Photo/video policy

[ ] Media check-in

[ ] Interview availability

[ ] Non-profit/legal description

[ ] Where proceeds/reinvestment go

[ ] Sponsors/partners

[ ] Cancellation/weather plan

[ ] Public contact

[ ] Media-only contact

[ ] Last updated / version

## Image and media specifications

| Asset | Minimum useful standard |
| --- | --- |
| Hero editorial photograph | JPEG, preferably 3000 px or more on the long edge; uncluttered landscape composition; no poster text over faces; clear credit and names left-to-right. |
| Print portrait/headshot | High-resolution JPEG; ideally 2400 px or more on long edge; neutral and expressive options; colour plus optional monochrome. |
| Web/social crops | 16:9 landscape (1920x1080), 1:1 square (1080x1080) and 4:5 vertical (1080x1350). Supply clean photos and separate designed art. |
| Logo | SVG plus transparent PNG, large enough for print; light and dark versions; no embedded personal data or outdated tagline. |
| B-roll | 1080p or 4K H.264 MP4; 20-90 seconds of clean, stable, rights-cleared footage; horizontal master plus selected vertical clips; no copyrighted music unless cleared. |
| Audio | WAV 48 kHz/24-bit master plus 320 kbps MP3; clean voice clips; 15/30/60-second versions; pronunciation guide. |
| Documents | DOCX, accessible/tagged PDF where possible, and plain-text/HTML version. Editors often paste from email, so never make the PDF the only text source. |
| Email payload | Keep attachments minimal; use a stable media-kit link. One small hero image may be attached when useful. Do not send a large ZIP unsolicited. |
| File naming | 1140A_[EventSlug]_[YYYY-MM-DD]_[Asset]_[Name-or-View]_[Credit].ext; avoid "final-final-v2". |
| Captions/rights | Every image and clip has a caption, names, location/date, photographer/creator, mandatory credit and explicit editorial-use permission. |

## The copy block that lets an outlet publish quickly

Place the following fields, in this order, in a clean text file and on the media-kit webpage. This is a specification, not drafted copy.

[ ] Publishable headline (factual, under roughly 12 words) and optional subheading.

[ ] Cape dateline and 35-60-word lead containing event, date, venue/town and significance.

[ ] 100-150 words of event and mission context.

[ ] One founder quote and one talent/venue/community quote.

[ ] Each featured comic's one-line proof point plus link to approved biography.

[ ] Exact ticket line, age/content line and accessibility line.

[ ] 60-90-word organisation boilerplate.

[ ] Media contact and stable media-kit URL.

[ ] Photo caption and credit directly below the copy.

[ ] Version and issue date so an editor knows which facts are current.

# 4. The safe public website media package

Use a permanent, un-gated address such as /press or /media/[event-slug]. Make the page easy to view on a telephone and let editors download individual files without creating an account.

## Public download page - include

[ ] Current press release as webpage text, accessible PDF and DOCX.

[ ] One-page media advisory after it is issued.

[ ] Event fact sheet with version/date.

[ ] 25-, 50-, 100-, 150- and 250-word approved descriptions.

[ ] Organisation boilerplate and approved founder biography.

[ ] Approved short/medium biographies for announced talent only.

[ ] High-resolution, rights-cleared photographs with captions and credits; individual downloads plus a modest ZIP.

[ ] Logo pack (SVG and transparent PNG) with clear-space/usage note.

[ ] B-roll and clean short clips through reliable, non-expiring download links.

[ ] Radio copy and clean audio clips if genuinely useful.

[ ] Ticket link, age/content guidance, accessibility, parking and venue information.

[ ] Media contact using a role-based email such as press@[domain]; optional dedicated press telephone, not a home/personal number.

[ ] Review/credential request link with a clear deadline and no promise of approval.

[ ] Last-updated stamp, corrections contact and a concise editorial-use licence.

## Do not place in the public kit

[ ] Personal home address, personal mobile number, private email, date of birth, tax identifiers, signatures or governance documents not intended for publication.

[ ] Talent or venue contracts, fees, riders, hotel details, travel itineraries, green-room location, security plans or backstage access instructions.

[ ] Unannounced line-up, draft billing, internal disputes, cancellation contingencies or quotes not finally approved.

[ ] Ticket barcodes, comp codes, credential QR codes, seat holds or files that could facilitate counterfeiting or unauthorised access.

[ ] Unlicensed television clips, music, press photographs, screenshots, archive clippings or comedy material.

[ ] Tax-deductibility, charity or 501(c)(3) claims that have not been specifically approved.

[ ] Internal attendance targets, budget, donor data, mailing list, outlet notes, embargo list, interview aversion or assessment of individual journalists.

[ ] A full-resolution ZIP so large that it fails on mobile; offer both individual assets and a reasonable bundle.

## Recommended public page layout

| Page area | Content |
| --- | --- |
| Top of page | Event title; date; venue/town; one-sentence description; ticket button; media contact; "last updated". |
| Fast facts | A clean two-column fact block that can be copied without formatting problems. |
| Approved copy | Short description tabs or clearly labelled blocks: 25 / 50 / 100 / 150 / 250 words. |
| Talent | Headshot, exact name, 50-word biography, key credits, pronunciation and download link. |
| Images | Thumbnail gallery showing aspect ratio, photographer, names and rights. Download original without opening a social-media post. |
| Video/audio | Embedded preview plus direct download; shot list/transcript and rights line. |
| Organisation | Mission, legal description, boilerplate and founder/spokesperson biography. |
| Press attendance | Credential/review request, deadline, contact, accessibility and photography rules. |
| Footer | Editorial-use terms, correction contact, privacy policy and stable archive link after the event. |

Editorial-use licence wording to have counsel approve • Assets may be used without charge solely for bona fide editorial coverage of The 1140-A Company and the named event, with the supplied credit and without misleading alteration. • Commercial advertising, merchandise, artificial-intelligence training, resale and third-party redistribution are not included unless separately authorised. • The licence should identify the actual rights-holder and any asset-specific restrictions.

# 5. What each media type expects

The directory uses the pack codes below. Build these variants once, then tailor the opening note and local relevance.

| Code | Use for | What they need from you | Lead time / follow-up |
| --- | --- | --- | --- |
| D-NEWS | Daily newspaper / major news site | Personal pitch; 350-500-word release in email body; fact sheet; one hero photo; links to talent proof; exact local hook; named spokesperson. | Pitch 4-8 weeks out; follow once after 4-5 working days; advisory 48-72 hours out. |
| W-LOCAL | Weekly / hyperlocal paper | Ready-to-run 200-350-word local brief; venue-town resident/partner quote; 1-3 captioned photographs; calendar facts; print-friendly deadline awareness. | 6-8 weeks when possible; many close several days before print. |
| CAL | Calendar / listings desk | Structured fields only: title, date/time, venue/address, price, age, 50/100/150-word copy, image, ticket URL, contact. No manifesto. | Submit as soon as public; re-check approval 7-10 days later. |
| MAG | Magazine / long-lead lifestyle | Story pitch rather than release; distinctive mission/talent/travel angle; excellent photography; seasonal relevance; evidence of broader trend. | 8-16 weeks or more; issue dates may close months ahead. |
| BUS | Business / non-profit / economy | Organisation launch, governance/legal status, funding model, local spend, jobs/partners and measurable mission. Avoid unsupported impact projections. | 4-10 weeks; use actual figures and named business partner. |
| R-COM | Commercial radio | 30-60-second pitch; 15/30/60 announcer copy; pronunciation; talent availability; giveaway proposal; clean audio clip; ticket URL. | 3-6 weeks; follow programme producer/promotions, not only newsroom. |
| R-PUB | Public/community radio | Editorial public-interest angle, Cape culture/history, thoughtful guest, tape-ready audio and community relevance. Separate PSA/community-calendar request. | 4-8 weeks for features; PSA deadlines often 2-4 weeks. |
| TV | Commercial television / cable news | Visual story pitch; 20-90 seconds b-roll; two articulate interviewees; live-shot logistics; parking/power; short advisory and exact availability. | Feature pitch 2-6 weeks; assignment desk again 48-72 hours out. |
| CTV | Community television / PEG | PSA/community notice, event slide, 15/30-second copy, local resident/venue tie, interview offer and rights-cleared video. | 3-6 weeks; town eligibility and non-commercial rules vary. |
| REV | Reviewer / critic / arts writer | Independent invitation, two seats where possible, full artist material, start/finish, photo policy, no gift beyond access, no positive-coverage expectation. | Invite 3-5 weeks out; confirm attendance 3-5 days out. |
| TRAVEL | Tourism / chamber / visitor guide | Visitor utility: date, town, lodging/dining adjacency, weather-proof plan, booking link, accessibility and polished image. Member rules may apply. | 4-12 weeks; calendar first, editorial pitch only if genuine travel story. |
| WIRE | Wire / national desk | Only a genuine wider-news peg: first-of-kind evidence, notable talent news, data/trend, public-interest issue or nationally relevant Cape story. Full verification pack. | Pitch under embargo only by agreement; generic local-event copy will not travel. |
| ID | Identity / language / community outlet | Authentic connection to talent, founder, audience, partner or language; translated copy by a competent human; specific community value; correct names and context. | 4-8 weeks; never use as a token blast. |
| STUDENT | College / student media | Student/alumni/talent tie, affordable access, transport, age policy, short copy, interview with comic and two-seat review invitation. | 3-6 weeks; respect academic calendars and holidays. |
| $DIST | Paid distribution / sponsored listing | Final proofed release, exact categories/geography, rights-cleared image, landing page and tracking links. Label paid/sponsored placement accurately. | After personal first wave; do not confuse pickup reports with earned coverage. |

## Daily and weekly newspapers: the plug-and-play standard

• Put the local reason in the subject and first sentence: venue town, Cape resident, non-profit mission, talent's Massachusetts tie or historical evidence.

• Paste a clean release below a 70-120-word personalised note. Attachments are optional; a stable link is essential.

• Give editors several lengths. The 250-word brief is often more useful than a long release.

• Offer exact captions and a horizontal photograph without text. Posters are poor editorial images.

• Use named, available sources. A quotation alone is not a substitute for interview access.

• For weeklies, learn the print day and closing time. A release sent after deadline may wait a full week.

• For reviews, invite the arts editor separately rather than hiding a comp offer in the mass release.

## Radio: editorial, community diary, PSA and promotion are different asks

• News/talk pitch: the Cape culture/non-profit story, a strong comic guest and concise talking points.

• Community diary: 50-100 words, exact date/time/place/price/link, submitted through the station's designated form or inbox.

• PSA: eligibility may require qualifying non-profit status and prohibits sales-heavy language. Ask for the current rules before recording.

• Promotion/ticket giveaway: define number of pairs, entry period, fulfilment, age restriction, data/privacy responsibility and on-air mentions. Keep editorial and promotional decisions separate.

• Recorded interview: offer a technically clean remote line, quiet room, headphones, backup telephone and a 10-minute window if the founder prefers short appearances.

• Pronunciation sheet: organisation name, venue and every performer, with a simple phonetic rendering and audio link.

## Television: make the story visual before asking for airtime

• Provide usable pictures now: stage set-up, venue exterior, Cape establishing shots you own, audience arrival only with appropriate releases, and clean comic clips.

• Offer two people who can carry the segment: ideally a featured comic and the founder/venue/community partner. The founder can choose a short pre-recorded slot or written Q&A where appropriate.

• State what a crew can film, at what time, with what sound/light, and whether a live shot is possible.

• Send a one-page advisory 48-72 hours out with VISUALS and INTERVIEWS near the top.

• Do not use copyrighted broadcast footage from a comic's television credit as b-roll without permission; link producers to the source for reference only.

• For a day-of news hit, a real "why today" is needed: opening night, final ticket release, community allocation, venue transformation or measurable milestone.

## Public media: pitch a story, not a sales message

• Lead with cultural history, Cape community, artist economics, audience access or a thoughtful talent story; the ticket link is supporting information.

• Explain the public value and the tension/question: why did the Cape fall off some touring routes, what makes a room work for comedy, or how can a mission-led producer build a sustainable circuit?

• Offer intelligent guests and tape, not a demand for free promotion.

• Disclose the organisation's financial interest and any sponsorship. Do not offer comps as leverage for editorial coverage.

• Use the station's community-calendar/PSA route separately from a programme pitch.

## Founder interview-light strategy

| Primary approach | Offer written email Q&A with a same-day turnaround and an approved fact sheet. |
| --- | --- |
| Broadcast option | Offer a tightly bounded 8-10 minute pre-recorded interview rather than an open-ended live appearance. |
| Alternative voices | Featured comic, venue representative, local arts/community partner, historian or board representative. |
| Quote discipline | Prepare 6-8 natural, fact-bearing quote themes; never require a journalist to use supplied quotations. |
| On-camera preparation | Three messages, two examples, one invitation; practise a 20-second answer and a 90-second answer. |
| Availability wording | "The founder is available for written Q&A and selected brief interviews; talent and venue spokespeople are also available." |
| Risk | If no credible human source is available, major feature and broadcast prospects fall sharply. At least one articulate spokesperson must be genuinely reachable. |

# 6. Email, follow-up and launch sequence

## The email architecture

| Element | Recommended practice |
| --- | --- |
| From | A named person at a role-based domain address, e.g. [Name] <press@[domain]>. Authenticate the domain and test delivery before launch. |
| Subject | Specific outlet + local hook + date. Example structure only: "Cape non-profit launches [event] at [venue] - [talent/angle]". Avoid ALL CAPS and "huge announcement". |
| Opening | One sentence showing why this outlet or audience is relevant. Personalise with recent coverage only when genuinely connected. |
| Pitch paragraph | 70-120 words: what is happening, why it matters now, the Cape/local angle, strongest proof and exact interview/visual offer. |
| Practical line | Date, venue/town, ticket link, age/content guidance, media-kit link and best contact. |
| Release | Paste the approved release beneath a divider or link to the text. Never make an editor open a PDF to learn the basics. |
| Attachment | At most one small, useful hero image unless the outlet asks otherwise. Put full-resolution assets behind the link. |
| Close | A clear, low-pressure ask: listing, preview, interview, segment, reviewer invitation or confirmation of the correct desk. |
| Compliance | Keep a record of public-source origin, bounces and opt-outs; stop repeated pitching when asked. A press blast should still be respectful and traceable. |

## Subject-line formula bank - structures, not final copy

• [Venue town] resident/non-profit launches [event] at [venue] on [date]

• Cape Cod comedy tradition gets a new chapter with [talent/event]

• Calendar: [event] - [date], [venue/town], [price range]

• Interview/preview: [comic] brings [current credit/angle] to Cape Cod

• Visual feature: transforming [venue] for a 300-plus-seat comedy event

• Public-service/community diary: non-profit comedy event on [date]

• Review invitation: [event], [date], [venue] - two press seats available

• Post-event: [verified attendance/result] at inaugural Cape comedy event

## Recommended sequence once talent and venue are confirmed

| When | Action |
| --- | --- |
| Before public announcement | Final approvals; ticket page live but unlisted if possible; media kit staged; first-wave emails loaded; calendar fields copied; photo rights signed; spokesperson rehearsed. |
| Optional 24-48-hour pre-pitch | One carefully chosen Cape/local or Boston outlet may receive an exclusive or embargoed look only if it has explicitly agreed. Never put "embargoed" on an unsolicited blast and assume consent. |
| Announcement morning | Publish ticket/media pages; send A-priority personal emails first; submit venue-town and Cape-wide calendars; post owned channels after journalists have received the material. |
| Same day afternoon | Send radio, community television, chambers, tourism calendars and B-priority regional outlets; log every route and error. |
| Day 2-3 | Send statewide, identity/community (where relevant), student/alumni and national long shots; use paid distribution only after personal targets have had a fair first look. |
| Day 4-7 | One concise follow-up to high-value editorial targets with a new fact, interview window, talent clip or early sales/community milestone. Do not send "just checking in". |
| 3-4 weeks out | Reviewer invitations; ticket giveaways; confirm calendar appearance; pitch deeper features and radio interviews. |
| 10-14 days out | Second news peg: venue transformation, local partnership, added community allocation, verified talent milestone or historical archive item. |
| 48-72 hours out | Visual media advisory to TV, radio news, daily newsrooms, community television and attending reviewers; re-confirm interview and press check-in. |
| Event day | Short assignment-desk note only if there is a genuine visual/new fact; no broad spam. Deliver approved photos rapidly. |
| Within 12-24 hours after | Send attending media an accurate photo/caption sheet, corrected facts, attendance range only when verified and next concrete milestone. |
| Within 3-5 days after | Post-event results note to non-attending targets; archive coverage; thank journalists without asking for favourable language; update proof deck for event two. |

## Follow-up rules

[ ] Follow once after roughly four to five working days for features; calendars may need a status check after seven to ten days.

[ ] Add a reason: new clip, interview window, venue detail, local partner, verified ticket milestone or deadline. Do not merely resend the same release.

[ ] Telephone only assignment desks, time-sensitive producers or contacts who invite calls. Respect stated "email only" preferences.

[ ] If an outlet declines or does not respond after one useful follow-up, move on until the 72-hour advisory or a genuinely new development.

[ ] Correct errors promptly and privately first; provide exact replacement wording and source. Keep a correction log.

[ ] Do not use read-receipt pressure, deceptive "Re:" subjects, fake personal familiarity or undisclosed mass-mail merge errors.

## Deliverability and data hygiene

• Send from the organisation's own domain, not a brand-new free address; configure SPF, DKIM and DMARC and test before the announcement.

• Use a named sender and functioning reply address. Monitor bounces and immediately fix the list rather than repeatedly sending to dead inboxes.

• Keep first-wave batches small enough to personalise and monitor. BCC is acceptable for low-priority public calendar routes but not for priority editorial pitches.

• Store the public source URL and date for each contact. Avoid buying unverified personal data or scraping private addresses.

• Use normal text, one clear link domain and modest attachments; excessive tracking links, image-only email and large ZIP files raise spam risk.

• Maintain an opt-out/suppression field even though editorial outreach is not an ordinary marketing newsletter.

# 7. Reviewer, critic and complimentary-ticket plan

## The ethical invitation

Core wording principle • Invite independent coverage; do not request or imply a positive review. Access is not payment for praise. • State clearly that two press seats are available, subject to confirmation; travel, accommodation and other benefits are not included unless specifically disclosed. • A reviewer must be free to attend without a pre-show interview or social post, and free to publish no piece at all.

## Who should receive review invitations

| Group | Priority and rationale |
| --- | --- |
| Cape arts and local press | Cape Cod Times arts/entertainment, Cape Cod Chronicle, Provincetown Independent, Cape Cod Wave, CapeCod.com/CCB NewsCenter and the venue-town weekly. |
| Massachusetts arts critics | The Arts Fuse and relevant Boston Globe/Boston Herald/Boston.com/Boston Magazine arts or comedy writers when the talent and scale justify travel. |
| Regional independents | Plymouth Independent, New Bedford Light, SouthCoastToday/Standard-Times and islands papers where audience geography or talent ties make the trip plausible. |
| Public media | Invite for preview/interview or attendance, but do not frame a comp as an expectation of review; public-media ethics and staffing may limit acceptance. |
| Student critics | Only when a comic, founder or audience has a real college connection and transport/age rules are practical. |
| National comedy writers | Only for significant talent news, a distinctive non-profit model with wider implications, or evidence that the Cape circuit story is part of a national trend. |

## Review invitation contents

[ ] Personal note naming the writer's relevant beat or recent work; no flattery unrelated to the event.

[ ] Exact show date, doors/start/end, venue/town, seating type, age/content guidance and accessibility.

[ ] Two-seat offer by default, a response deadline and the name under which seats will be held.

[ ] Full line-up and billing order, talent biographies, current credits and clean photographs.

[ ] Photography and recording policy, including whether first minutes or house-approved images are available.

[ ] Press check-in time and on-site contact; no ticket barcode in ordinary email.

[ ] Interview options before/after the show, clearly optional and subject to artist approval.

[ ] Disclosure of any material relationship, sponsor, travel support or additional benefit.

[ ] A sentence confirming that coverage and viewpoint are entirely at the outlet's discretion.

## Press-seat operating policy

| Initial hold | Reserve a modest number of pairs, including wheelchair/companion flexibility, without damaging paid inventory. |
| --- | --- |
| Approval | Named press lead approves requests against outlet relevance, assignment evidence and capacity; avoid viewpoint discrimination. |
| Confirmation | Send a written confirmation with arrival time and check-in name; do not email transferable barcodes unless necessary. |
| No-show release | State when unclaimed seats may be released. Keep a telephone contact for delays. |
| Seating | Place reviewers where sound and sightlines are representative, not necessarily the best premium seats; disclose unusual restrictions. |
| Guest | Allow one guest where inventory permits. Do not demand the guest's personal data beyond ticketing needs. |
| Gifts | No swag, meals or value beyond ordinary press access unless modest, relevant and disclosed. Never condition access on social posting. |
| Corrections | After publication, request corrections only for verifiable factual errors, not taste, tone or criticism. |
| Archive | Record invitation, assignment/attendance, seats used, coverage link and any factual correction. |
| Future relationship | Thank the writer, preserve independence and keep them informed of the next genuinely relevant event. |

## Ticket giveaway checklist for radio and local media

[ ] Number and value of ticket pairs; exact performance; age restriction; accessibility; whether fees are waived.

[ ] Entry dates, eligibility area, minimum age, employee exclusions, winner selection, notification and redemption deadline.

[ ] Who collects entrant data and owns compliance/privacy responsibility.

[ ] Approved on-air description, pronunciation and ticket link; whether the station needs logo/art or recorded copy.

[ ] No requirement that winners post positively; no transfer/resale; clear replacement/cancellation rule.

[ ] A unique fulfilment code or will-call process that cannot expose the main comp inventory.

[ ] Written separation between promotional inventory and editorial coverage decisions.

# 8. Day-of media operations and post-event proof

## Day-of media desk

| Role / system | Minimum requirement |
| --- | --- |
| Press lead | Owns list, check-in, facts, corrections and media decisions; not simultaneously running front-of-house. |
| Talent liaison | Knows exact interview windows, dressing-room boundaries, pronunciation and who can approve clips/quotes. |
| Visual producer | Captures rights-cleared stills and b-roll, labels files and delivers a fast 5-10-image edit. |
| Venue contact | Handles crew parking, power, load-in, public areas, accessibility, house rules and emergency changes. |
| Spokesperson | Available in a quiet, lit location; has three messages and factual examples; knows what cannot be discussed. |
| Fact channel | One live document or message thread with running order, attendance status, changes and approved wording. |
| Press kit access | QR/short URL at check-in plus human help; never force a journalist to use a QR code. |
| Contingency | Prepared cancellation, delay, line-up-change, safety and weather wording; immediate update to ticket/media pages. |

## 72-hour visual advisory fields

[ ] WHAT: exact event and the new reason it is timely now.

[ ] WHO: talent and available interviewees with one-line credentials.

[ ] WHEN: media arrival, interview window, doors, show and end.

[ ] WHERE: full address, media entrance, parking/load-in and live-shot position.

[ ] VISUALS: venue transformation, stage, soundcheck, exterior, audience arrival (subject to consent) and performance limits.

[ ] AUDIO: clean comedy clip/soundcheck opportunities and quiet interview area.

[ ] ACCESS: credential deadline, check-in, accessibility and restrictions.

[ ] CONTACT: one continuously monitored mobile number and email.

[ ] LINKS: ticket page and direct b-roll/photo download.

[ ] CHANGES: line-up and timing confirmed at [timestamp].

## Post-event proof package

[ ] Five to ten edited photographs within hours, with complete captions and credits.

[ ] A concise verified attendance statement: exact scanned count, range, percentage or "near capacity" only if defensible.

[ ] One audience reaction and one talent/venue reaction collected with permission; avoid anonymous superlatives.

[ ] Any measurable community result: local partner, community seats used, funds reinvested, local staffing or next confirmed milestone.

[ ] Links to published coverage and broadcast clips where lawful; screenshots for internal proof, not redistribution.

[ ] Corrections or line-up changes plainly noted.

[ ] One forward-looking line: next date, open talent submission, venue search or mission milestone only when genuinely confirmed.

[ ] Updated media kit retained at the same URL, with the event labelled "past" rather than removed.

## What to measure

| Measure | Record |
| --- | --- |
| Reach activity | Personal pitches sent; calendar submissions; valid/bounced contacts; follow-ups; interview offers; reviewer invitations. |
| Earned results | Original stories, briefs, listings, interviews, broadcast segments, reviews and syndicated pickups - counted separately from paid placement. |
| Quality | Headline/message accuracy, Cape/non-profit hook used, talent credits included, image quality, ticket link and correction rate. |
| Commercial signal | Referral traffic by outlet, ticket conversions where trackable, giveaway redemption and sales timing; do not overclaim causation. |
| Relationship | New named contacts, response preferences, future interest and topics/lead times requested. |
| Mission proof | Artist experience, audience feedback, community access, local partnerships and concrete reinvestment. |
| Future value | Assets and evidence that make the second event easier to cover: professional photographs, attendance, quotes, clips and press links. |

# 9. Prioritised Cape Cod and Massachusetts media directory

This is intentionally over-inclusive. Routes and personnel change frequently; re-open every official link and confirm the current editor, producer, calendar or public-service policy before sending. Direct public emails are included where they were clearly published; otherwise use the official route and identify the current beat holder.

Pack-code shorthand • D-NEWS daily/major newsroom; W-LOCAL local weekly; CAL calendar; MAG magazine; BUS business/non-profit; R-COM commercial radio; R-PUB public/community radio; TV television; CTV community television; REV review; TRAVEL tourism/chamber; WIRE national/wire; ID community/language; STUDENT student; $DIST paid distribution. • Timing in the tables is a planning target, not a guarantee. Calendar and print deadlines take precedence.

## 9A. Cape Cod print, digital and magazine outlets

Start with the venue-town outlet, then Cape-wide media. "Legacy" rows are included because the brief asked for an over-inclusive list; they should not consume launch-day time unless verified.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| A | Cape Cod Times | Cape-wide daily; lead with Cape benefit, inaugural scale, talent proof and venue-town relevance. Separate arts/editorial pitch from calendar submission. | V: public newsroom email; official help/contact page. Identify current arts/entertainment editor before launch. news@capecodonline.com Official page | D-NEWS + CAL; 4-8 weeks, then 72-hour advisory. | Yes - arts/review invitation; two seats. |
| A | Cape Cod Chronicle | Key Lower/Outer Cape weekly for Chatham, Harwich and Orleans. Strong venue-town, resident, history and local-partner angle. | V: public newsroom route; check current print deadline and arts/calendar instructions. news@capecodchronicle.com Official page | W-LOCAL + CAL + REV; 6-8 weeks. | Yes when venue/audience fit. |
| A | Provincetown Independent | Outer Cape weekly with substantial arts coverage. Best for Provincetown/Truro/Wellfleet/Eastham or distinctive Cape culture/history. | V: arts notices requested at least two weeks before publication; use arts desk and confirm current format. arts@provincetownindependent.org Official page | W-LOCAL + CAL + REV; 3-8 weeks. | Yes - strong arts/review prospect. |
| A | The Enterprise / CapeNews group | Falmouth, Mashpee, Bourne and Sandwich weeklies. Promote the matching title to first priority when the venue is in its town. | V/H: central newsroom/contact route; specify exact Enterprise edition and local connection. newsroom@capenews.net Official page | W-LOCAL + CAL + REV; 6-8 weeks. | Yes for venue-town title. |
| A | CapeCod.com / CCB NewsCenter | Cape-wide digital newsroom attached to Cape Cod Broadcasting; natural bridge to news, calendar and three radio stations. | V: official news-submission form; send event separately to calendar/promotions where relevant. Official page | D-NEWS + CAL + R-COM; 4-6 weeks. | Preview/interview more likely than formal review. |
| A | Cape Cod Wave | Independent Cape culture/reporting site; best for an intelligent founder, place, artist-economics or Cape-history feature. | V/H: public contact route. Pitch a reported story, not a generic release. capecodwave@gmail.com Official page | D-NEWS + MAG + REV; 4-10 weeks. | Yes - thoughtful feature/review invite. |
| $ | Cape Cod Daily News | Paid regional press-release posting/distribution; useful as a searchable link and secondary amplification, not proof of earned editorial coverage. | V: paid submission with stated turnaround; confirm current fee and category. Official page | $DIST after first-wave personal pitches. | No comp; paid placement. |
| C | Cape Wide News | Breaking-news/public-safety site. A routine event release is usually a poor fit; use only for a real news development, disruption or public-safety advisory. | V: public tips route; site states routine press releases are not its focus. Official page | D-NEWS only for genuine breaking/public-interest fact. | No routine review invitation. |
| B | Cape Cod Life Publications | Cape lifestyle and visitor readership; strong for a long-lead mission, seasonal culture, venue or talent profile with excellent photography. | V/H: official contact/editorial route; confirm issue lead time and whether event listings are accepted. Official page | MAG + TRAVEL; 8-16 weeks or more. | Feature/preview; review less likely. |
| B | Cape & Plymouth Business Media | Business/non-profit launch, cultural-economy, founder, venue partnership, local employment or reinvestment angle. | H: official contact; identify current editor and provide figures, governance facts and partner voices. Official page | BUS; 4-10 weeks. | No comp initially; invite if feature develops. |
| B | Love Live Local | Cape local-business/non-profit community and newsletter audience. Best for local ownership, reinvestment, partnerships and resident-first value. | V: event-submission form and direct contact; membership/eligibility may affect promotion. Official page | CAL + BUS + TRAVEL; as soon as public. | No reviewer comp; possible giveaway/partner. |
| B | Provincetown Magazine | Arts, culture and visitor readership; strongest if venue, talent or audience has an Outer Cape/LGBTQ+ connection. | H: official contact; check seasonal issue calendar and event-listing route. Official page | MAG + CAL + REV; 8-16 weeks. | Conditional review/feature. |
| C | Provincetown Arts | Arts journal with long lead; use only for a serious comedy-as-art, Cape cultural-history or artist-profile angle. | H: editorial/submission route; not a routine event calendar. Official page | MAG; months ahead. | No routine comp; feature only. |
| B | Cape Cod Star | Cape arts-and-entertainment listings and features; useful for structured event information and local arts angle. | V/H: submit through official calendar/contact route and verify current editorial schedule. Official page | CAL + W-LOCAL; 4-8 weeks. | Conditional review invitation. |
| C | Guidebook Cape Cod | Visitor-oriented event and destination site; practical listing, good image and ticket link matter more than organisational background. | V: public "submit event" route; check fees/eligibility. Official page | TRAVEL + CAL; 4-8 weeks. | No review comp. |
| C | CapeDays | Cape events/visitor calendar; useful long-tail listing for residents and visitors. | V: official event-submission route; use concise structured copy. Official page | CAL + TRAVEL; as soon as public. | No review comp. |
| C | WeNeedaVacation.com Cape Cod events | High-intent holiday-rental audience; best for summer visitor utility and advance booking. | V/H: official event/calendar route; check listing rules and seasonality. Official page | TRAVEL + CAL; 4-12 weeks. | No review comp. |
| C | Edible Cape Cod | Only when food, hospitality, local restaurant partnership or venue culinary story is genuinely central. | H: editorial contact; do not force an unrelated event pitch. Official page | MAG + TRAVEL; long lead. | Conditional feature invite. |
| C | Patch Massachusetts - Cape/local editions | Hyperlocal digital network. Select the venue town, founder town or talent hometown edition; calendar and community-post routes may differ. | H: official local page/contact; identify current editor and use Patch event tools where available. Official page | W-LOCAL + CAL; 3-6 weeks. | Conditional review/preview. |
| D | Barnstable Patriot | Legacy Barnstable paper/brand. Potentially relevant for Barnstable venue or founder tie, but current publication/submission status must be confirmed. | H: official support/contact page; do not rely on legacy addresses without testing. Official page | W-LOCAL + CAL only after verification. | Conditional if active. |
| D | Cape Codder / Wicked Local Cape titles | Legacy Lower Cape/Gannett routes may still surface in search or local pages. Treat as a verification task, not an assumed active newsroom. | H: search current USA TODAY Network/Wicked Local contact page and confirm title, editor and calendar before sending. Official page | W-LOCAL + CAL only if active. | Conditional if active. |
| D | Cape Cod Today | Legacy digital brand; verify current publishing activity, ownership and contact before inclusion in any blast. | H: do not send until a recent article and functioning editorial route are confirmed. Official page | D-NEWS/CAL only if active. | No comp until verified. |

## 9B. Cape Cod radio and audio

Send the station-specific request even when several stations share a group. A newsroom pitch, calendar entry, PSA request and ticket giveaway are four different workflows.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| A | CAI - Cape, Coast & Islands NPR | Cape Cod, Martha's Vineyard, Nantucket and SouthCoast public radio. Pitch Cape culture/history and the non-profit model; submit PSA/community material separately. | V: general contact plus public-service announcement route. Offer a smart guest or written briefing, not a sales read. cai@capeandislands.org Official page | R-PUB + CAL; 4-8 weeks; PSA 2-4 weeks. | Preview/interview; comp only if requested. |
| A | WQRC 99.9 The Q | Cape Cod Broadcasting adult audience; community calendar, morning-show guest, giveaway or NewsCenter story through the group. | V: Cape Cod Broadcasting contact/calendar; specify station and ask for promotions/programme producer. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/preview, not review. |
| A | WKPE Cape Country 104 | Cape Cod Broadcasting country audience; local resident/venue, community benefit and ticket-pair promotion. | V: group contact; specify Cape Country 104 and promotion/community diary request. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| A | WOCN Ocean 104.7 | Cape Cod Broadcasting adult contemporary/older audience; strong fit for a grown-up night out and low-profanity positioning when accurate. | V: group contact; specify Ocean 104.7. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/host interview. |
| A | WPXC PIXY 103 | Coxswain Media classic-rock/general Cape audience; community calendar, morning show and ticket giveaway. | V/H: Coxswain Media official station/contact route; specify PIXY 103. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/host mention. |
| A | 93.5 / 93.9 Frank FM | Coxswain Media adult/classic hits audience; venue-town utility, ticket pairs and concise announcer copy. | V/H: Coxswain Media group contact; specify Frank FM. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| A | Y101 Cape Cod | Coxswain Media current-hits audience; best when talent has strong social/podcast reach or younger-adult appeal. | V/H: group contact; specify Y101 and relevant programme/promotions. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/interview. |
| A | Koffee FM 98.7 / 100.5 | Coxswain Media adult audience; practical community diary and grown-up night-out angle. | V/H: group contact; specify Koffee FM. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| A | 95 WXTK | Cape news/talk station; strong for founder interview, Cape cultural-history angle, community calendar and talent conversation. | V/H: iHeart Cape Cod contact; target newsroom/talk producer and public-service route separately. Official page | R-COM/D-NEWS + CAL; 3-6 weeks. | Interview/giveaway. |
| A | 106 WCOD | Cape iHeart music station; lifestyle/morning-show promotion and ticket giveaway. | V/H: station/iHeart contact; identify local promotions or morning producer. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| A | Cool 102 (WCIB) | Cape iHeart classic-hits audience; older/adult demographic and community-event utility. | V/H: station/iHeart contact; submit community information and promotion request separately. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| B | 96.3 WEII | Cape sports audience; possible talent sports tie, morning show, sponsor or ticket giveaway. Weak without a genuine connection. | V/H: iHeart Cape Cod group route; specify WEII. Official page | R-COM; 3-6 weeks. | Giveaway only if fit. |
| A | WOMR 92.1 / WFMR 91.3 | Community radio serving Provincetown and Orleans; strong for Outer Cape, community diary/Town Crier, arts interview and non-profit public service. | V: community calendar/contact routes; concise copy and real community relevance. Official page | R-PUB + CAL; 3-6 weeks. | Interview; comp if requested. |
| B | WGTX X102.3 | Outer Cape commercial station; local calendar, personality mention and giveaway, especially for Lower/Outer Cape venue. | H: official station contact; identify local programme/promotions. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| B | WKKL 90.7 / WSDH 91.5 - Cape Cod Community College | College/community audience and possible student/alumni angle. Confirm current format, staffing and submission route each term. | H/D: college station or communications contact; academic calendar matters. Official page | R-PUB + STUDENT; 3-6 weeks. | Student interview/review invite. |
| C | Cape Cod radio cluster public-affairs programmes | Some commercial stations fulfil public-affairs obligations through weekend programmes. A non-profit mission and Cape cultural question may fit better here than in a music show. | H: ask station group for current public-affairs producer and submission deadlines; do not assume PSA eligibility. Official page | R-COM/R-PUB; 4-8 weeks. | Interview, no review expectation. |

## 9C. Cape Cod community television and local video

Promote the venue-town service to A priority. Community channels often require local eligibility, advance notice and non-commercial wording.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| A | Cape Media Center | Community media for Barnstable, Yarmouth, Dennis, Harwich and Chatham; venue-town interview, PSA, calendar, studio programme or event coverage where eligible. | V/H: official contact and community programming route; town/service eligibility and non-commercial rules apply. Official page | CTV + CAL; 3-6 weeks. | Preview/interview; press seats if assigned. |
| A | Falmouth Community Television (FCTV) | First-wave community television when venue, founder, partner or audience is in Falmouth. | V/H: official contact; ask for community bulletin, PSA, interview and coverage policies. Official page | CTV + CAL; 3-6 weeks. | Preview/recorded interview. |
| A | Sandwich Community Television | First-wave service for Sandwich venue/community tie; bulletin and local interview potential. | V/H: official contact; confirm eligibility and event-slide specifications. Official page | CTV + CAL; 3-6 weeks. | Preview/interview. |
| A | Mashpee TV | First-wave service for Mashpee venue, resident or community partner. | V/H: official contact; send non-commercial 15/30-second copy and image. Official page | CTV + CAL; 3-6 weeks. | Preview/interview. |
| A | Bourne Community TV | First-wave service for Bourne/Canal venue or founder tie; local bulletin and studio interview. | V/H: official contact; confirm municipal/community calendar rules. Official page | CTV + CAL; 3-6 weeks. | Preview/interview. |
| A | Lower Cape TV | Community media serving Lower Cape towns; strong for Orleans/Eastham/Wellfleet/Truro area and Cape culture/history. | V/H: official contact; pitch interview plus event notice and rights-cleared visuals. Official page | CTV + CAL; 3-6 weeks. | Preview/coverage; reviewer if assigned. |
| A | Provincetown Community Television | Provincetown-specific community service; strong for Outer Cape/LGBTQ+ and arts audience. | V/H: official contact; confirm bulletin/programme requirements. Official page | CTV + CAL; 3-6 weeks. | Preview/interview. |
| B | Venue-town municipal video/public-information channel | Some towns maintain separate government channels or newsletters beyond PEG programming. Use only for public-service/community information accepted under local policy. | H: town communications office; commercial ticket language may be restricted. Official page | CTV/CAL; 3-6 weeks. | No reviewer comp. |

## 9D. Cape Cod calendars, chambers and non-editorial amplifiers

These routes can produce discovery rather than journalism. Label them correctly in reporting. A calendar listing, chamber newsletter or paid feature is not earned news coverage.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| A | ArtsCapeCod / Arts Foundation of Cape Cod | The Cape's arts calendar and cultural network. Essential listing and possible editorial/newsletter amplification for an arts event. | V: official submit-event form; follow required fields and image specifications. Official page | CAL; submit immediately when public. | No review comp; partnership invite only. |
| A | CapeCod.com events calendar | Cape-wide consumer calendar linked to CCB media. Submit independently of the NewsCenter pitch. | V: official add-event route; concise copy, image, link and accurate category. Official page | CAL; immediately when public. | No review comp; radio promotion separate. |
| A | CapeEvents.com | Cape-wide event discovery; useful for residents and visitors and easy to overlook in a newsroom-only plan. | V: official add-event route; check paid/featured options separately from basic listing. Official page | CAL + TRAVEL; immediately when public. | No review comp. |
| A | Cape Cod Chamber of Commerce / Visit Cape Cod | Regional visitor audience, destination calendar and possible travel-story/industry amplification. Member and tourism criteria may apply. | V/H: official event/contact route; lead with visitor utility and Cape-wide benefit. Official page | TRAVEL + CAL; 6-12 weeks. | No review comp; partner invitation possible. |
| A | Cape Cod Radio Cape Calendar | Coxswain Media calendar serving multiple stations; use structured community copy and then pitch programme/promotions separately. | V/H: submit through Cape Cod Radio calendar/contact route. Official page | CAL + R-COM; 3-6 weeks. | No review comp. |
| A | WOMR Town Crier / community calendar | Outer Cape community listing and possible on-air read. | V: station community route; short non-commercial copy. Official page | CAL + R-PUB; 3-6 weeks. | No review comp. |
| B | ArtsBarnstable | Barnstable arts/culture calendar and visitor resource; A priority for Barnstable/Hyannis venue or partner. | V/H: official event calendar/contact; confirm eligibility and lead time. Official page | CAL + TRAVEL; 4-8 weeks. | No review comp. |
| B | Hyannis Main Street / Hyannis BID | Downtown Hyannis audience and business network; strong only for Hyannis venue, restaurant partnership or walkable-night-out story. | H: official contact/calendar/newsletter; member/area rules may apply. Official page | CAL + TRAVEL + BUS; 4-8 weeks. | Partner/giveaway, not review. |
| B | Massachusetts Office of Travel and Tourism - VisitMA | Statewide travel/event discovery; useful for summer and shoulder-season visitors once date/venue are public. | V/H: official event submission or regional tourism route; follow eligibility and image rules. Official page | TRAVEL + CAL; 6-12 weeks. | No review comp. |
| C | Cape Cod Museum Trail calendar/network | Only if partnering with a member museum/cultural institution or making a documented Cape cultural-history connection. | H: contact network; do not submit a routine commercial event without fit. Official page | CAL/TRAVEL; 6-10 weeks. | Partner invitation only. |
| C | Cape Cod Young Professionals | Newsletter/community network for younger professionals; founder/non-profit, volunteering, affordable-access or local-economy angle. | H: official contact; newsletter/event eligibility may require membership/partnership. Official page | BUS + CAL; 4-8 weeks. | Giveaway/partner, not review. |
| A | Cape Cod Canal Region Chamber | Bourne/Canal visitor and business audience; A priority for Bourne venue. | H: official events/contact page; membership rules may apply. Official page | TRAVEL + CAL + BUS; 4-8 weeks. | Partner/giveaway. |
| A | Falmouth Chamber of Commerce | Falmouth visitor/business calendar; A priority for Falmouth venue. | H: official calendar/contact; provide image and visitor utility. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Mashpee Chamber of Commerce | Mashpee visitor/business network; A priority for Mashpee venue. | H: official events/contact page; check member rules. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Sandwich Chamber of Commerce | Sandwich visitor/business network; A priority for Sandwich venue. | H: official event/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Greater Hyannis Chamber of Commerce | Hyannis/Barnstable business and visitor audience; A priority for Hyannis venue. | H: official calendar/contact; check eligibility. Official page | TRAVEL + CAL + BUS; 4-8 weeks. | Partner/giveaway. |
| A | Yarmouth Chamber of Commerce | Yarmouth visitor calendar and business network; A priority for Yarmouth venue. | H: official calendar/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Dennis Chamber of Commerce | Dennis visitor/business calendar; A priority for Dennis venue. | H: official events/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Harwich Chamber of Commerce | Harwich visitor/business audience; A priority for Harwich venue. | H: official calendar/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Brewster Chamber of Commerce | Brewster visitor/business network; A priority for Brewster venue. | H: official events/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Chatham Chamber of Commerce & Merchants Association | Chatham visitor/business calendar; A priority for Chatham venue. | H: official calendar/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Orleans Chamber of Commerce | Orleans visitor/business audience; A priority for Orleans venue. | H: official calendar/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Eastham Chamber of Commerce | Eastham visitor/business audience; A priority for Eastham venue. | H: official calendar/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Wellfleet Chamber of Commerce | Wellfleet visitor/business audience; A priority for Wellfleet venue. | H: official calendar/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Truro Chamber of Commerce | Truro visitor/business audience; A priority for Truro venue. | H: official contact/calendar; site may route through community events. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| A | Provincetown Chamber of Commerce | Provincetown visitor/business audience; A priority for Provincetown venue and summer traveller reach. | H: official events/contact; member/area rules may apply. Official page | TRAVEL + CAL; 4-8 weeks. | Partner/giveaway. |
| B | Venue-town local cultural council | Each Cape town has a local cultural council/network. Useful for cultural legitimacy, partner voices and community amplification, not usually an editorial newsroom. | V/H: use Mass Cultural Council directory to find venue-town council; ask before submitting promotional material. Official page | CAL/partner; 6-10 weeks. | Partner invitation, no review expectation. |
| B | Venue-town municipal calendar/newsletter | Potential public information route when venue/partner is municipal or the event meets local community-calendar rules. Commercial-ticket events may be excluded. | H: use official town website/communications office; do not assume acceptance. Official page | CAL/CTV; 4-8 weeks. | No review comp. |
| C | Town libraries and councils on ageing - partner route | Not a media blast target. Include only with a real partnership, group-ticket offer or age-appropriate community programme. | H: venue-town institution; use community relations, not press-release spam. Official page | Partner/calendar; 6-10 weeks. | Group invitation only. |
| C | Cape lodging concierge and visitor newsletters | Non-editorial amplification for summer guests; best through chamber/hotel relationships and a concise, commission-free event sheet. | H: direct partner outreach after public announcement; respect individual property policies. Official page | TRAVEL; 4-8 weeks. | Giveaway/concierge preview only if appropriate. |

## 9E. Martha's Vineyard and Nantucket

The islands are relevant but not automatic. Pitch the audience/travel/talent connection explicitly; do not pretend a mainland Cape event is local island news.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| B | The Martha's Vineyard Times | Island newspaper with arts/calendar coverage; plausible for Cape visitors, talent ties or a wider islands/Cape cultural story. | V/H: official contact/newsroom and calendar route; identify arts editor. Official page | W-LOCAL + CAL + REV; 6-8 weeks. | Yes if travel/fit is realistic. |
| B | Vineyard Gazette | Martha's Vineyard newspaper and magazine group; strong writing/photography expected and a genuine island/Cape connection is needed. | V/H: official editorial/contact and calendar route; long lead for magazine. Official page | W-LOCAL/MAG + CAL + REV; 6-16 weeks. | Conditional review/feature. |
| C | Martha's Vineyard Magazine / Complete MV | Seasonal lifestyle/visitor audience; use travel, culture and talent profile angle with excellent images. | H: Gazette group/editorial contact; check seasonal issue deadline. Official page | MAG + TRAVEL; 8-16 weeks. | Feature, not routine review. |
| B | MVYRADIO | Island-focused non-commercial/community station with Cape reach; cultural interview, calendar and talent conversation. | V/H: official contact/community calendar; pitch public value. Official page | R-PUB + CAL; 4-8 weeks. | Interview; comp if assigned. |
| C | WVVY-LP Martha's Vineyard Community Radio | Community radio; use only with island audience/talent/partner connection and confirm current operations. | H: official site/contact; verify current schedule and submission route. Official page | R-PUB + CAL; 3-6 weeks. | Interview/mention. |
| C | MVTV - Martha's Vineyard Community Television | Community television; local eligibility may limit a mainland Cape event unless there is an island partner or talent tie. | H: official contact and programme rules. Official page | CTV + CAL; 3-6 weeks. | Preview/coverage if assigned. |
| C | Martha's Vineyard Chamber of Commerce | Visitor calendar; useful for island residents travelling to Cape or a wider regional itinerary. | H: official calendar/contact; membership rules may apply. Official page | TRAVEL + CAL; 6-10 weeks. | No review comp. |
| B | Nantucket Current | Digital Nantucket newsroom; use only for a strong regional/talent/travel connection or a notable non-profit cultural story. | V/H: official contact/news tips; send concise local relevance. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional review/feature. |
| B | The Inquirer and Mirror | Nantucket newspaper with arts/calendar/visitor audience; genuine connection required. | V/H: official contact/calendar route; identify arts editor. Official page | W-LOCAL + CAL + REV; 6-8 weeks. | Conditional review invite. |
| C | N Magazine | Nantucket lifestyle magazine; long-lead talent, travel or regional cultural trend only. | H: official editorial contact; polished photography essential. Official page | MAG + TRAVEL; 8-16 weeks. | Feature only. |
| C | 97.7 ACK FM | Nantucket commercial/community station; practical calendar/giveaway if island travel audience is plausible. | H: official station contact; confirm local promotions/community diary. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| C | Nantucket Community Television | Community channel; local eligibility likely requires island partner or community tie. | H: official contact/programme route. Official page | CTV + CAL; 3-6 weeks. | Preview if assigned. |
| C | Nantucket Island Chamber of Commerce | Visitor calendar and member network; long-shot for a mainland Cape event unless packaged as regional travel or partner offer. | H: official events/contact page. Official page | TRAVEL + CAL; 6-10 weeks. | No review comp. |

## 9F. Plymouth, South Shore and SouthCoast

These are the most plausible off-Cape regional audiences. Venue/talent hometown connections dramatically improve the odds; say exactly why the event is relevant to their readers or listeners.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| B | Plymouth Independent | Independent Plymouth newsroom; strong for a Cape/Plymouth cultural-economy, resident, venue or talent connection and for readers within driving distance. | V/H: official newsroom/contact; identify arts/community editor. Official page | W-LOCAL/D-NEWS + CAL + REV; 4-8 weeks. | Yes - preview/review invite. |
| B | Old Colony Memorial / Wicked Local Plymouth | Legacy/local Plymouth title within the USA TODAY Network; verify current editor and submission route. | H: current official contact/help page; do not use stale staff emails. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional review. |
| B | The Patriot Ledger | South Shore daily; plausible for a regional entertainment, founder/talent tie or visitor-drive story. | H: USA TODAY Network official contact; identify features/entertainment desk. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional review/preview. |
| C | The Enterprise (Brockton) | South Shore/Metro South daily; use for a talent hometown, founder, partner or broad regional entertainment story. | H: official contact; identify current features desk. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| B | Wareham Week | Immediate gateway community to Cape Cod; strong driving-distance audience and venue/talent relevance. | V/H: official Week Today contact/event route; provide ready-to-run local brief. Official page | W-LOCAL + CAL + REV; 4-8 weeks. | Yes if geography fits. |
| B | Sippican Week | Marion, Mattapoisett and Rochester weekly; relevant for Upper Cape/SouthCoast audiences and local talent/partner ties. | V/H: official contact/calendar route. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional review. |
| C | Dartmouth Week | SouthCoast weekly; use with Dartmouth/New Bedford talent, student, audience or partner tie. | V/H: official contact/calendar route. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | Nemasket Week | Middleborough/Lakeville area; long-tail driving-distance audience and talent hometown route. | V/H: official contact/calendar route. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| B | The Wanderer | Mattapoisett, Marion and Rochester community paper; local culture and regional event listing. | H: official contact; submit local relevance and clean photo. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional review. |
| B | New Bedford Light | Non-profit local newsroom; strong for non-profit cultural infrastructure, artist economics, SouthCoast/Cape audience or talent ties. | V/H: official newsroom contact; pitch public-interest story, not promotion. Official page | D-NEWS + BUS + REV; 4-8 weeks. | Yes if story relevance is strong. |
| B | The Standard-Times / SouthCoastToday | Regional daily for New Bedford/SouthCoast; event calendar, entertainment and driving-distance audience. | H: USA TODAY Network contact; identify features/entertainment desk. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional review/preview. |
| C | New Bedford Guide | Large regional digital/community audience; use structured listing, strong visual and SouthCoast connection. | H: official contact/submit route; clarify editorial versus sponsored options. Official page | D-NEWS + CAL; 3-6 weeks. | Conditional preview/giveaway. |
| C | Fall River Reporter | Digital regional news; use with Fall River/talent/partner or SouthCoast cultural angle. | H: official contact/news tip route. Official page | D-NEWS + CAL; 3-6 weeks. | Conditional. |
| C | The Herald News (Fall River) | Regional daily; driving-distance audience and talent/partner tie. | H: USA TODAY Network contact; current features/community desk. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional review. |
| C | Taunton Daily Gazette | Regional daily; use for talent hometown, partner or South Shore/SouthCoast audience. | H: official contact; identify features desk. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| B | WATD 95.9 | South Shore news/community radio with local interviews, public affairs and calendar; good bridge audience into Cape. | V/H: official contact and community calendar; target relevant programme producer. Official page | R-COM/R-PUB + CAL; 3-6 weeks. | Interview/giveaway. |
| B | WBSM 1420 | New Bedford news/talk; non-profit/cultural discussion, founder or comic guest and community calendar. | V/H: official contact; pitch programme producer and promotions separately. Official page | R-COM + CAL; 3-6 weeks. | Interview/giveaway. |
| B | Fun 107 | SouthCoast music/morning-show audience; ticket giveaway and talent/podcast/social angle. | V/H: official contact/promotions; concise announcer copy. Official page | R-COM + CAL; 3-6 weeks. | Giveaway/mention. |
| C | WJFD 97.3 Portuguese Radio | Portuguese-language SouthCoast audience. Use only with an authentic Lusophone talent, founder, partner or translated-access angle. | H: official contact; provide professionally translated Portuguese copy. Official page | ID + R-COM; 4-8 weeks. | Interview/giveaway if fit. |
| B | PACTV - Plymouth Area Community Television | Community television for Plymouth-area audience; interview, bulletin and local culture programme. | H: official contact; town eligibility/programme rules apply. Official page | CTV + CAL; 3-6 weeks. | Preview/interview. |
| C | WFNX-LP 101.3 Scituate Community Radio | Community station for South Shore audience; calendar and interview only with driving-distance/local connection. | H: official contact; confirm current community-calendar process. Official page | R-PUB + CAL; 3-6 weeks. | Interview/mention. |
| C | South Shore Home, Life & Style | Regional lifestyle magazine; long-lead grown-up night-out, Cape travel and cultural experience angle. | H: official editorial/contact; polished photography and seasonal timing. Official page | MAG + TRAVEL; 8-16 weeks. | Feature/preview. |
| C | South Coast Almanac | Regional magazine/storytelling; use for a deeper Cape/SouthCoast cultural trend or founder feature, not a calendar-only blast. | H: editorial contact; confirm current publishing schedule. Official page | MAG + BUS; long lead. | Feature invite. |
| C | South Coast Insider | Regional arts/lifestyle publication; possible event listing or feature with SouthCoast relevance. | H: official contact and current publication schedule. Official page | MAG + CAL; 6-12 weeks. | Conditional review. |
| B | See Plymouth / Plymouth County tourism | Visitor calendar and regional itinerary; useful for travellers combining Plymouth and Cape. | H: official event/contact route; strong visitor utility. Official page | TRAVEL + CAL; 6-10 weeks. | No review comp. |
| B | Plymouth Area Chamber of Commerce | Business/visitor newsletter and calendar; use for Plymouth-Cape regional audience or partner. | H: official event/contact route; member rules may apply. Official page | TRAVEL + CAL + BUS; 4-8 weeks. | Partner/giveaway. |
| C | South Shore Chamber of Commerce | Business network; use for corporate/group sales, venue partnership or regional cultural-economy story rather than routine editorial. | H: official events/contact; membership rules apply. Official page | BUS + TRAVEL; 6-10 weeks. | Partner invitation. |
| C | One SouthCoast Chamber | Regional business/visitor network; use for SouthCoast partner, talent or economic angle. | H: official event/contact; member rules apply. Official page | BUS + CAL; 6-10 weeks. | Partner invitation. |
| C | Explore New Bedford calendar | Visitor/event discovery for New Bedford audiences; use concise driving-distance utility. | H: official event/contact route. Official page | TRAVEL + CAL; 4-8 weeks. | No review comp. |

## 9G. Boston and statewide print, digital, arts and community outlets

Boston outlets are not "local" to the Cape. The pitch must justify the trip: notable talent, a Massachusetts trend, Cape destination value, a strong non-profit model or a meaningful Boston/talent connection.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| B | The Boston Globe | Massachusetts' highest-impact general outlet. Needs a specific arts, Cape, travel, business/non-profit or talent news peg; a routine event listing is insufficient. | V/H: official newsroom/contact/tips route; identify current arts, comedy, travel, New England or business reporter and pitch personally. Official page | D-NEWS/MAG + REV; 6-12 weeks. | Yes, selectively; two seats and full materials. |
| B | Boston.com | Consumer-oriented things-to-do, culture and travel audience; stronger for accessible event utility, breakout talent and Cape weekend planning. | H: official contact/current things-to-do editor; check event submission options. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional preview/review. |
| B | Boston Herald | Statewide tabloid/general news and entertainment; lead with talent recognition, Cape scale, strong image and concise practical facts. | V/H: official newsroom/contact; identify current entertainment/features editor. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional review/preview. |
| B | Boston Magazine | Longer-lead lifestyle, "best of", weekend and people coverage. A notable talent, Cape trend or distinctive non-profit model is needed. | H: official masthead/contact; target appropriate editor rather than general blast. Official page | MAG + REV; 8-16 weeks. | Feature/review selectively. |
| B | Boston Business Journal | Organisation launch, funding, governance, sponsorship, cultural-economy and founder story. Requires credible figures and business relevance. | H: official newsroom/contact; identify current non-profit/arts/business reporter. Official page | BUS; 4-10 weeks. | No comp initially; invite if assigned. |
| B | The Arts Fuse | Independent New England arts criticism; one of the best off-Cape review targets when the line-up and artistic proposition are strong. | H: official contact/editorial route; pitch the comedy as an arts event and offer independent access. Official page | REV + MAG; 4-8 weeks. | Yes - priority critic invitation. |
| C | Universal Hub | Boston-area independent news/community site. Cape event is a long shot unless there is a strong Boston talent, founder or audience connection. | H: official contact/tips route; concise, specific link to Boston. Official page | D-NEWS + CAL; 3-6 weeks. | Conditional. |
| C | DigBoston | Alternative culture audience; verify current editorial activity and comedy/arts contact immediately before sending. | H: current website/contact and recent publication check required. Official page | D-NEWS/MAG + REV; 4-8 weeks. | Conditional review if active. |
| C | Vanyaland | New England entertainment/culture site; music-heavy but can cover broader culture and talent. Best with notable comic or Boston tie. | H: official contact/editorial route. Official page | D-NEWS + REV; 4-8 weeks. | Conditional preview/review. |
| C | The Boston Calendar | Greater Boston event calendar; Cape geography may be outside normal scope, but worth testing for a major event or Boston-weekend audience. | V/H: official submit-event route; follow geography and listing rules. Official page | CAL; 4-8 weeks. | No review comp. |
| C | ArtsBoston / BosTix | Greater Boston arts network and calendar/ticketing ecosystem. Cape event may be out of service area unless partnership/eligibility exists. | H: official contact; ask whether Cape listings or organisational membership qualify. Official page | CAL/TRAVEL; 6-12 weeks. | No review comp. |
| C | Yankee Magazine / NewEngland.com | Regional travel/lifestyle long shot. Needs a wider New England trend, Cape tradition, destination itinerary or exceptional talent profile. | H: official editorial/contact; long lead and premium images. Official page | MAG + TRAVEL; 12-24 weeks. | Feature only. |
| C | New England Living | Regional lifestyle programme/publication; Cape culture, venue, founder and destination story with excellent visuals. | H: official contact and current editorial schedule. Official page | MAG/TV + TRAVEL; 8-16 weeks. | Feature invite. |
| B | MassLive / The Republican | Large statewide/western Massachusetts digital reach; strong only with notable talent, Massachusetts-wide trend or western-Mass connection. | V/H: official tips/contact; identify entertainment/statewide reporter. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional review/preview. |
| C | CommonWealth Beacon | Public-policy/non-profit newsroom. Not an event-listing target; use only for a substantive policy, cultural-infrastructure or non-profit-economics story. | H: official editorial contact; pitch evidence and public-interest question. Official page | BUS/D-NEWS; 6-12 weeks. | No comp unless assigned. |
| C | State House News Service | Policy/news service used by Massachusetts media. Only relevant if the organisation/event creates a real state policy, funding, tourism or non-profit-sector story. | H: official newsroom/contact; never send routine entertainment release as if it were State House news. Official page | BUS/WIRE; as news warrants. | No comp. |
| C | Worcester Business Journal | Business/non-profit and cultural-economy story with Central Massachusetts talent/partner or statewide trend. | H: official newsroom/contact; figures and named partners. Official page | BUS; 4-10 weeks. | No comp initially. |
| C | BusinessWest | Western Massachusetts business publication; only with western-Mass talent, sponsor or state-wide non-profit/economy angle. | H: official editorial contact. Official page | BUS; 6-12 weeks. | No comp initially. |
| C | Bay State Banner | Boston Black community newspaper. Use only with an authentic Black talent, founder, partner, audience or community-benefit connection. | H: official contact/editorial route; specific community relevance. Official page | ID + D-NEWS + REV; 4-8 weeks. | Conditional review/preview. |
| C | Bay Windows | New England LGBTQ+ newspaper. Strong with LGBTQ+ talent, founder, partner or Provincetown/Cape community connection. | H: official editorial/contact route. Official page | ID + D-NEWS + REV; 4-8 weeks. | Conditional review/preview. |
| C | The Rainbow Times | New England LGBTQ+ publication. Use only with a direct talent/community/partner relevance. | H: official contact/submission route. Official page | ID + D-NEWS; 4-8 weeks. | Conditional review. |
| C | Boston Spirit Magazine | LGBTQ+ lifestyle magazine. Strongest with Provincetown/Cape, talent or community partnership; long lead. | H: official editorial/contact. Official page | ID + MAG; 8-16 weeks. | Feature/review selectively. |
| C | El Mundo Boston | Spanish-language/community outlet. Use only with Spanish-speaking talent, translated access, partner or clear Latino audience value. | H: official contact; provide professionally translated Spanish copy and spokesperson if available. Official page | ID + D-NEWS + CAL; 4-8 weeks. | Interview/giveaway if fit. |
| C | El Planeta | Spanish-language New England publication. Use authentic community connection and human-quality translation. | H: official editorial/contact route. Official page | ID + D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | Sampan | Asian American community newspaper. Use only with an authentic talent, partner, audience or community connection. | H: official editorial/contact route; be specific and respectful. Official page | ID + D-NEWS; 4-8 weeks. | Conditional review/preview. |
| C | Brazilian Times | Portuguese-language/Brazilian community publication. Use with a genuine Brazilian/Lusophone connection and professional Portuguese copy. | H: official contact/editorial route. Official page | ID + D-NEWS + CAL; 4-8 weeks. | Interview/giveaway if fit. |
| C | Portuguese Times | Portuguese-American newspaper serving Massachusetts/Rhode Island. Use with a real Lusophone or SouthCoast connection. | H: official contact/editorial route; Portuguese copy strongly preferred. Official page | ID + D-NEWS; 4-8 weeks. | Conditional. |
| C | O Jornal | Portuguese-language community newspaper. Use only with a real talent/community/partner tie. | H: official contact and current publication check. Official page | ID + D-NEWS; 4-8 weeks. | Conditional. |
| C | India New England News | Indian/South Asian New England publication. Use with authentic talent, partner or audience relevance. | H: official contact/editorial route. Official page | ID + D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | JewishBoston | Community culture/events platform. Use with Jewish talent, partner, date/holiday context or authentic community story. | H: official contact/submit-event route; calendar rules apply. Official page | ID + CAL + D-NEWS; 4-8 weeks. | Conditional review/preview. |
| C | Jewish Journal | Greater Boston/North Shore Jewish newspaper. Use with authentic community/talent connection. | H: official editorial/contact route. Official page | ID + D-NEWS; 4-8 weeks. | Conditional. |
| C | The Boston Pilot | Catholic newspaper. Use only with a genuine Catholic/non-profit/community partner or talent story; adult-content framing must be candid. | H: official editorial contact. Official page | ID + D-NEWS; 4-8 weeks. | Conditional. |
| C | The Armenian Weekly | Armenian-American publication. Use only with authentic talent/founder/community relevance. | H: official editorial contact. Official page | ID + D-NEWS; 4-8 weeks. | Conditional. |
| C | The Haitian Reporter | Boston Haitian community publication. Use only with an authentic community/talent/partner connection and appropriate language access. | H: Dorchester Reporter group contact; confirm current route. Official page | ID + D-NEWS; 4-8 weeks. | Conditional. |
| C | Boston Seniority / 50-plus community media | Potential adult audience for a less profanity-driven night out. Use accurate content guidance, accessibility and transport information. | H: current senior/ageing publication or council newsletter; choose geography and partner relevance. Official page | ID + CAL; 4-8 weeks. | Group/giveaway, not critic review. |

## 9H. Boston and Massachusetts television, radio and public media

For broadcast, the "route" is often an assignment desk, programme producer, community calendar, promotions department or public-affairs producer - not one universal inbox. Send a visual/audio-ready, programme-specific ask.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| B | WBUR 90.9 / WBUR News | Boston NPR newsroom with statewide/New England reach. Pitch Cape culture, non-profit model, artist economics or notable talent; Here & Now is a separate national long shot. | V: public newsroom email and official contact. Identify current arts/culture or relevant programme producer. wburnews@wbur.org Official page | R-PUB/D-NEWS; 6-10 weeks. | Interview/feature; comp only if requested. |
| B | GBH News | Boston public media newsroom; statewide cultural/public-interest story, strong visuals/audio and credible guest. | V: public news email/contact; distinguish newsroom from programme-specific pitches. wgbhnews@wgbh.org Official page | R-PUB/TV + D-NEWS; 6-10 weeks. | Interview/feature; comp if assigned. |
| B | GBH The Culture Show | Highly relevant arts programme. Pitch comedy as art/culture, Cape tradition and talent trajectory; offer a thoughtful guest and clips. | V: programme email on official contact page. thecultureshow@wgbh.org Official page | R-PUB + REV; 4-8 weeks. | Priority interview/preview invite. |
| B | GBH Boston Public Radio | Conversation-driven public radio. Use a wider Cape culture, live-entertainment or non-profit question with articulate guests. | V/H: official programme contact; concise topic and guest credentials. Official page | R-PUB; 4-8 weeks. | Interview; no review expectation. |
| B | WCVB NewsCenter 5 | Major television newsroom. Needs current visual hook, notable talent or strong Cape public-interest/local story. | V: official contact/tip route. Send feature pitch early and visual advisory 48-72 hours out. Official page | TV; 2-6 weeks + advisory. | Segment/coverage, not formal review. |
| A | WCVB Chronicle | Excellent fit for a distinctive Cape culture/history/non-profit/talent feature with strong visuals and human story. | V: public programme email on WCVB contact page; send a story proposal, not a release dump. chronicle@wcvb.com Official page | TV/MAG; 6-12 weeks. | Priority feature invitation. |
| B | WCVB 5 For Good | Strong if the non-profit model has a concrete, measurable community benefit beyond selling tickets. | V: public programme email. Provide legal status, beneficiaries, numbers and partner voice. 5forgood@wcvb.com Official page | TV + BUS; 4-10 weeks. | Feature; no quid pro quo comp. |
| B | WCVB Made in Mass | Possible if The 1140-A Company's Massachusetts-built model, local supply chain or cultural entrepreneurship is distinctive. | V: public programme email on WCVB contact page. madeinmass@wcvb.com Official page | TV + BUS; 6-10 weeks. | Feature invitation. |
| C | WCVB CityLine | Use only with an authentic Black community, talent, founder, partner or access angle. | V: public programme email; community relevance must be specific. cityline@wcvb.com Official page | TV + ID; 4-8 weeks. | Feature/interview. |
| B | WBZ-TV / CBS News Boston | Major television newsroom; strong visual event, notable comic, Cape travel story or genuine milestone. | V: public news-tip email/contact. Include b-roll and 72-hour advisory. newstips@wbztv.com Official page | TV; 2-6 weeks + advisory. | Segment/coverage. |
| B | WHDH 7News | Fast-paced television newsroom; current news/visual hook and concise logistics. | V: official contact/tip route; use assignment desk for time-sensitive advisory. Official page | TV; 2-4 weeks + advisory. | Segment/coverage. |
| B | Boston 25 News | Major television newsroom; Cape local-interest, notable talent, visual event or community story. | V: official news-tip form/contact; deliver usable video and interview windows. Official page | TV; 2-6 weeks + advisory. | Segment/coverage. |
| B | NBC10 Boston | Major television newsroom; visual Cape/event/talent story and timely advisory. | V/H: official tips/contact. Identify current assignment desk/feature producer. Official page | TV; 2-6 weeks + advisory. | Segment/coverage. |
| B | The Hub Today - NBC10 Boston | Lifestyle/daytime programme; especially strong for comedy preview, weekend Cape itinerary and on-camera comic guest. | H: official programme/contact route; send segment concept, visuals and guest availability. Official page | TV + TRAVEL; 4-8 weeks. | Priority lifestyle segment. |
| B | NECN | Regional cable news with New England reach; use larger Cape/New England trend, notable talent or visual story. | H: NBC Boston/NECN tips/contact; identify assignment desk. Official page | TV; 2-6 weeks + advisory. | Segment/coverage. |
| B | Spectrum News 1 Massachusetts | Statewide cable news and community calendar; Worcester-based but covers Massachusetts stories and events. | V: official story/contact and submit-event route. Official page | TV + CAL; 3-6 weeks. | Segment/preview. |
| C | Telemundo Nueva Inglaterra | Spanish-language television. Use with Spanish-speaking talent, partner, audience or translation/access story. | H: official contact/news tips; provide Spanish materials and spokesperson. Official page | TV + ID; 4-8 weeks. | Interview/giveaway if fit. |
| C | Univision Nueva Inglaterra | Spanish-language television/digital. Authentic Latino community connection and Spanish-language interview capacity needed. | H: official local contact/news tip route. Official page | TV + ID; 4-8 weeks. | Interview/segment if fit. |
| B | WBZ NewsRadio 1030 | Statewide news radio; short news item, community/public-affairs interview or notable talent. A generic event promotion is weak. | H: official iHeart contact/news tip route; identify newsroom/public affairs. Official page | R-COM/D-NEWS; 3-6 weeks. | Interview/mention. |
| C | WERS 88.9 | Emerson College/non-commercial station with arts audience. Use talent/music/culture, student/alumni or public-affairs connection. | H: official contact/programme route; academic calendar matters. Official page | R-PUB + STUDENT; 4-8 weeks. | Interview/review invite. |
| C | WUMB 91.9 | UMass Boston public music station. Comedy is outside core format, but public-affairs/community calendar or guest tie may fit. | H: official contact; identify current community/public affairs route. Official page | R-PUB + STUDENT; 4-8 weeks. | Conditional interview. |
| C | WCRB Classical 99.5 / GBH Music | Low fit unless event has arts-infrastructure, composer/music or cross-arts connection. Do not send routine blast. | H: GBH Music contact and calendar only with real fit. Official page | R-PUB/MAG; 6-10 weeks. | No routine comp. |
| C | WICN 90.5 Worcester | Public/community jazz station; possible arts interview, public-affairs or Central Mass talent connection. | H: official contact/programme route. Official page | R-PUB; 4-8 weeks. | Interview if fit. |
| C | NEPM - New England Public Media | Western Massachusetts public media. Needs western-Mass talent/partner or statewide culture/non-profit trend. | V/H: official news/contact route; programme-specific pitch. Official page | R-PUB/TV; 6-10 weeks. | Interview/feature. |
| C | WAMC Northeast Public Radio | Regional public radio reaching western Mass/New York. Use only for notable talent or wider regional culture/economics story. | H: official contact/newsroom/programme route. Official page | R-PUB; 6-10 weeks. | Interview/feature. |
| C | WWLP 22News | Western Massachusetts television; only with western-Mass talent/partner or statewide hook. | H: official contact/news tip route. Official page | TV; 2-6 weeks. | Segment if fit. |
| C | Western Mass News (WGGB/WSHM) | Western Massachusetts television; genuine regional tie required. | H: official contact/tips. Official page | TV; 2-6 weeks. | Segment if fit. |
| C | WCVB/WMUR overlap and New England assignment desks | A strong Cape tourism or New England talent story may interest adjacent-market television; use only with a clear audience link. | D: use current Massachusetts Broadcasters Association directory and official station sites. Official page | TV; 2-6 weeks. | Segment if fit. |
| C | Commercial Boston radio groups - iHeart, Audacy, Beasley | Morning shows, local public-affairs, promotions and giveaways. Target station/format and producer; do not blast every music station indiscriminately. | D/H: use group/station contacts and MBA directory. Offer 15/30/60 copy and tickets. Official page | R-COM; 3-6 weeks. | Giveaway/guest, no review. |
| C | College/community radio sweep | WMBR, WHRB, WZBC, WTBU, WBRS, WECB and similar stations; use only with student/alumni, age/price and transport fit. | D/H: official station/programme contact each academic term. Official page | STUDENT + R-PUB; 3-6 weeks. | Student interview/review. |

## 9I. Massachusetts regional and hyperlocal newspapers

This is the "one-in-a-million" layer. Do not send every outlet the same Cape pitch. Select the editions tied to the venue, founder, talent, partner, college or audience geography.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| C | Telegram & Gazette (Worcester) | Central Massachusetts daily. Use only with notable talent, Central Mass connection or statewide entertainment/non-profit trend. | H: USA TODAY Network official contact; identify current features/entertainment reporter. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional review/preview. |
| C | The Berkshire Eagle | Berkshire County daily with strong arts culture. A notable comedian, Massachusetts arts trend or Berkshire tie is required. | H: official newsroom/contact; identify arts editor. Official page | D-NEWS/MAG + REV; 6-10 weeks. | Conditional review. |
| C | Daily Hampshire Gazette | Hampshire County daily/arts audience. Use with western-Mass talent/college/alumni or statewide cultural trend. | H: official contact; identify arts/calendar desk. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional review. |
| C | Greenfield Recorder | Franklin County daily; western-Mass talent/partner or statewide non-profit/culture angle. | H: official contact; local relevance essential. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| D | Athol Daily News | North Quabbin community daily; one-in-a-million unless talent/founder/partner has a direct local tie. | H: official contact; send only with direct relevance. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | The Lowell Sun | Merrimack Valley daily. Use with talent hometown, partner or broad Massachusetts entertainment story. | H: official contact/newsroom; identify features desk. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional review. |
| C | Sentinel & Enterprise | North-central Massachusetts daily. Direct regional connection needed. | H: official contact/newsroom. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | The Eagle-Tribune | Merrimack Valley daily. Use with talent/partner/hometown or travel audience connection. | H: official contact; identify features/community desk. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | The Salem News | North Shore daily with arts/calendar coverage. Use with North Shore talent or Cape travel/seasonal story. | H: official contact; identify arts/features desk. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional review. |
| C | Gloucester Daily Times | Cape Ann daily; potential coastal-tourism comparison or talent tie, otherwise long shot. | H: official contact. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | The Daily News of Newburyport | North Shore/Merrimack coast audience; direct talent or travel relevance required. | H: official contact. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | The Daily Item (Lynn) | North Shore daily. Use with talent/community tie or statewide entertainment story. | H: official contact/newsroom. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | MetroWest Daily News | MetroWest USA TODAY Network daily; use with talent hometown/alumni, regional travel or statewide trend. | H: official contact; identify features desk. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional review. |
| C | Milford Daily News | MetroWest regional daily; direct talent/partner tie required. | H: official contact. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| D | The Gardner News | North-central regional paper; one-in-a-million without talent/partner connection. | H: official contact. Official page | D-NEWS + CAL; 4-8 weeks. | Conditional. |
| C | Community Advocate | Central Massachusetts community news network; use targeted town edition with talent, alumni or partner tie. | H: official editorial/contact and event routes. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional preview. |
| C | Worcester Guardian | Independent non-profit Worcester newsroom. Use for Central Mass talent/partner or statewide non-profit/cultural-infrastructure story. | H: official newsroom contact; public-interest angle required. Official page | D-NEWS + BUS; 4-8 weeks. | Conditional feature. |
| C | WHAV | Haverhill local news and radio outlet; direct Merrimack Valley talent/partner tie needed. | H: official newsroom/contact. Official page | D-NEWS + R-COM + CAL; 4-8 weeks. | Conditional interview. |
| C | Marblehead Current | Independent North Shore local newsroom; use only with local talent/resident/partner or specific Cape-travel readership angle. | H: official contact/news tips. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional review. |
| C | Ipswich Local News | Independent North Shore local outlet; direct local connection needed. | H: official contact/news tips. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | Brookline.News | Independent Brookline newsroom; talent/founder/alumni/local audience tie required. | H: official contact/news tips. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional review. |
| C | The Bedford Citizen | Independent local newsroom; direct resident/talent/partner tie only. | H: official contact. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | Lexington Observer | Independent local newsroom; direct resident/talent/alumni connection needed. | H: official contact/news tips. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | Needham Observer | Independent local newsroom; direct resident/talent/partner connection needed. | H: official contact. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | Fig City News (Newton) | Independent Newton newsroom; use with resident/talent/alumni/community tie. | H: official contact/news tips. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | The Newton Beacon | Independent Newton outlet; talent/founder/alumni connection or statewide non-profit trend. | H: official contact. Official page | W-LOCAL/D-NEWS; 4-8 weeks. | Conditional. |
| C | Cambridge Day | Independent Cambridge news/culture. Stronger with comedian, writer, founder, venue partner or university tie. | H: official contact/news tips. Official page | D-NEWS + CAL + REV; 4-8 weeks. | Conditional review/preview. |
| C | Watertown News | Independent local outlet; direct talent/resident/partner tie needed. | H: official contact. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | YourArlington | Independent Arlington news site; use with direct local/alumni/talent connection. | H: official contact/news tips. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | The Somerville Times | Local Somerville paper; useful with comic/arts-community/talent tie. | H: official contact. Official page | W-LOCAL + CAL + REV; 4-8 weeks. | Conditional review. |
| C | The Concord Bridge | Independent Concord newsroom; direct resident/talent/non-profit connection only. | H: official contact/news tips. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | Acton Exchange | Independent Acton newsroom; direct local/talent/alumni connection only. | H: official contact. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| D | The Belmont Voice | Independent local outlet; verify current operations and use only with direct local connection. | H: official contact and recent-publication check. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| C | Dorchester Reporter | Boston neighbourhood paper with strong community reporting; use with talent/resident/community or Cape travel connection. | H: official contact/newsroom. Official page | W-LOCAL + CAL + ID; 4-8 weeks. | Conditional review/preview. |
| D | Jamaica Plain Gazette | Neighbourhood paper; direct talent/resident/partner connection required. | H: official contact and current issue schedule. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| D | South Boston Online | Neighbourhood paper; use only with direct South Boston talent/resident/community connection. | H: official contact. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| D | Independent Newspaper Group - Boston-area titles | Charlestown Patriot-Bridge, East Boston Times-Free Press, Chelsea Record, Everett Independent, Revere Journal, Winthrop Sun Transcript, Beacon Hill Times and related titles. Use only for specific local ties. | H: group/individual title contact; identify exact community and editor. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| D | Gannett / Wicked Local Massachusetts title sweep | Numerous local titles and sections across Massachusetts. Select only talent/founder/partner hometowns; verify title activity and current editor. | D/H: USA TODAY Network/Wicked Local official pages; do not mass-send stale title lists. Official page | W-LOCAL + CAL; 4-8 weeks. | Conditional. |
| D | Massachusetts independent-local-news sweep | Use current local-news funding/network directories to identify newly launched outlets in the venue, founder and talent hometowns. | D: search current Press Forward/independent-news listings and official outlet sites. Official page | W-LOCAL/D-NEWS; 4-8 weeks. | Conditional. |
| D | NENPA New England newspaper directory / press release service | Coverage backstop across daily/weekly papers. The paid service advertises distribution to 156 New England newspapers; confirm current list and terms. | V: NENPA paid press-release distribution page; use after personal priority pitches. Official page | $DIST; allow stated processing time. | No comp; paid distribution. |

## 9J. Massachusetts student and college media

Student outlets can be highly responsive when there is a genuine alumni, age, price or subject-matter connection. Confirm that the event's admission rules and transport make the invitation realistic.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| B | Cape Cod Community College communications / student media | Closest college audience and potential local partnership, student ticket, alumni or workforce/cultural story. | H: college communications/student-life route; confirm current student publication and radio contacts. Official page | STUDENT + CAL + BUS; 4-8 weeks. | Student review/interview invite. |
| C | The Comment - Bridgewater State University | South Shore student audience; use with alumni/talent tie, affordable tickets and transport. | H: current student newspaper contact; academic calendar applies. Official page | STUDENT; 3-6 weeks. | Two-seat student review invite. |
| C | The Torch - UMass Dartmouth | SouthCoast student audience; use with talent/alumni/partner tie and realistic transport. | H: official student paper contact/current masthead. Official page | STUDENT; 3-6 weeks. | Student review/interview. |
| C | The Daily Free Press - Boston University | Boston student news/culture; best with BU alumni, young talent or comedy-industry angle. | H: official contact/masthead; pitch arts editor personally. Official page | STUDENT + REV; 3-6 weeks. | Two-seat review invite. |
| C | The Berkeley Beacon - Emerson College | Strong comedy/media/student fit, especially with Emerson alumni or emerging comics. | H: official contact; target arts/culture editor. Official page | STUDENT + REV; 3-6 weeks. | Priority student review/interview if tie. |
| C | The Huntington News - Northeastern University | Boston student news/culture; talent/alumni or young-adult audience tie. | H: official contact/masthead. Official page | STUDENT + REV; 3-6 weeks. | Student review/interview. |
| C | The Harvard Crimson | Long shot unless talent/founder has Harvard/Cambridge tie or there is a substantive arts/non-profit trend. | H: official tips/contact; identify arts or magazine editor. Official page | STUDENT + REV; 4-8 weeks. | Conditional review. |
| C | The Tufts Daily | Student arts/culture; talent/alumni or Boston-comedy connection needed. | H: official contact/masthead. Official page | STUDENT + REV; 3-6 weeks. | Student review/interview. |
| C | The Tech - MIT | Long shot; use with MIT/science/technology talent tie or unusual non-profit operating model, not generic event copy. | H: official contact. Official page | STUDENT; 4-8 weeks. | Conditional. |
| C | The Heights - Boston College | Student arts/culture; BC alumni/talent or audience tie needed. | H: official contact/masthead. Official page | STUDENT + REV; 3-6 weeks. | Student review. |
| C | The Justice - Brandeis University | Student arts/culture; alumni/talent connection or non-profit mission angle. | H: official contact/masthead. Official page | STUDENT + REV; 3-6 weeks. | Student review. |
| C | The Mass Media - UMass Boston | Boston public-university audience; talent/alumni, affordability or access angle. | H: official contact. Official page | STUDENT + REV; 3-6 weeks. | Student review/interview. |
| C | The Wellesley News | Long shot; use with alumni/talent/community tie and candid adult-content guidance. | H: official contact/masthead. Official page | STUDENT + REV; 3-6 weeks. | Conditional review. |
| C | The Massachusetts Daily Collegian - UMass Amherst | Large student audience; western-Mass talent/alumni or major statewide comedy story needed. | H: official contact; target arts/living editor. Official page | STUDENT + REV; 4-8 weeks. | Conditional review. |
| D | The Amherst Student | College paper; direct Amherst/talent/alumni tie required. | H: official contact. Official page | STUDENT; 4-8 weeks. | Conditional. |
| D | The Sophian - Smith College | Direct talent/alumni/community connection only. | H: official student paper contact. Official page | STUDENT; 4-8 weeks. | Conditional. |
| D | Mount Holyoke News | Direct talent/alumni/community connection only. | H: official student paper contact. Official page | STUDENT; 4-8 weeks. | Conditional. |
| D | The Williams Record | Direct Williams/Berkshires talent or alumni connection only. | H: official contact. Official page | STUDENT; 4-8 weeks. | Conditional. |
| D | The Scarlet - Clark University | Worcester student audience; talent/alumni or Central Mass connection. | H: official contact/current masthead. Official page | STUDENT; 3-6 weeks. | Conditional review. |
| D | The Spire - College of the Holy Cross | Worcester student audience; direct talent/alumni tie required. | H: official student paper contact. Official page | STUDENT; 3-6 weeks. | Conditional review. |
| D | Massachusetts college media sweep | Use talent biographies to search every performer's college, hometown and current city. Student papers and radio respond to a concrete alumni or affordability hook. | D/H: official university media directories and current mastheads; never blast a generic list. Official page | STUDENT; 3-6 weeks. | Two-seat review invite when appropriate. |

## 10. National, wire, comedy-trade and travel long shots

These targets are deliberately included because the brief requested even one-in-a-million opportunities. Do not send them a local calendar pitch. Build a distinct national or trade news peg, and research the current individual writer/producer before sending.

| P | Outlet / service | Coverage and best angle | Best public route | Pack / timing | Review or comp |
| --- | --- | --- | --- | --- | --- |
| C | Associated Press (AP) | Only for a genuine national/regional news peg: significant talent news, documented trend, unusual non-profit model, public-interest issue or major Cape tourism/culture story. | V/H: AP contact/tip routes and current Boston/New England bureau relationships. Do not expect a generic event release to be assigned. Official page | WIRE; fully verified pack; timing tied to actual news. | No comp unless a reporter requests access. |
| C | Reuters | Extremely long shot for a local event. Requires wider business, culture, tourism, creator-economy or non-profit trend with data and national relevance. | V: official tips/contact route; concise evidence and sources. Official page | WIRE; only with broad news peg. | No comp unless assigned. |
| C | Agence France-Presse (AFP) | International wire long shot; only with international talent, global tourism/culture trend or exceptional human-interest relevance. | H: official AFP contact/bureau route; verify current US desk. Official page | WIRE; only with international peg. | No comp unless assigned. |
| C | NPR national arts/culture | National public-radio long shot. Needs a wider story about comedy touring, regional culture, artist economics or a nationally notable comic. | H: NPR contact/tips and programme-specific producer; local CAI/WBUR/GBH first. Official page | WIRE/R-PUB; 6-12 weeks. | Interview/feature if assigned. |
| C | NPR Pop Culture Happy Hour | Only with a nationally relevant comedy subject, notable release/talent or broader cultural trend; not a routine event listing. | H: programme contact through NPR; pitch concept and guest, not ticket sales. Official page | R-PUB/WIRE; 6-12 weeks. | Feature/interview if fit. |
| C | Here & Now (WBUR/NPR) | National programme produced at WBUR. Strong only for a timely national culture, touring or non-profit innovation story with excellent guest. | H: official programme contact; concise segment idea and tape. Official page | R-PUB/WIRE; 4-10 weeks. | Interview if assigned. |
| C | PBS NewsHour / CANVAS arts coverage | One-in-a-million arts/culture target. Needs national significance, exceptional artist story or evidence of a wider cultural model. | V: official NewsHour contact/viewer email; identify current arts/CANVAS producer where possible. viewermail@newshour.org Official page | TV/WIRE; 8-16 weeks. | Feature if assigned; no routine comp. |
| C | The New York Times - Arts / Comedy | Only with nationally significant talent, trend or reported Cape/circuit story; identify a writer who has recently covered stand-up. | H: official tips/contact and individual beat research. Official page | WIRE/MAG + REV; 8-16 weeks. | Review/feature only if assigned. |
| C | The Washington Post - Style/Arts | National talent/trend or New England culture story required. | H: official newsroom contact/tips and current beat writer. Official page | WIRE/MAG; 8-16 weeks. | Feature if assigned. |
| C | USA TODAY Entertainment | National entertainment story only; notable talent, data/trend or unusual model. Gannett local network may be the more realistic route. | H: official newsroom/contact; identify comedy/entertainment reporter. Official page | WIRE/D-NEWS; 6-12 weeks. | Conditional. |
| C | Vulture / New York Magazine comedy coverage | Top comedy-industry target. Needs a comic with current national momentum, original industry news or a distinctive comedy-circuit story. | H: current comedy editor/writer through official masthead; personalised pitch only. Official page | MAG/REV/WIRE; 6-12 weeks. | Priority national critic invite only with strong talent. |
| C | Paste Magazine - Comedy | Comedy criticism/interviews; use for emerging-talent discovery and distinctive curated line-up. | H: current comedy editor/submission route; personalised pitch. Official page | MAG + REV; 4-10 weeks. | Review/interview invite. |
| C | The Comic's Comic | Specialist stand-up/comedy industry site; good for talent news, festival/television credits and unusual Cape circuit story. | H: official contact/social route; concise industry relevance. Official page | MAG + REV; 4-8 weeks. | Review/interview if feasible. |
| C | The Comedy Bureau | Comedy listings/news centred on major markets; Cape event is a long shot unless talent has national/NY/LA momentum or the model is distinctive. | H: official contact; pitch industry angle. Official page | MAG + REV; 4-8 weeks. | Conditional. |
| C | Chortle | UK-based comedy trade/news site with international reach. Use only for notable comedian, tour announcement, award/TV credit or unusual industry story. | H: official news/contact route; concise factual copy. Official page | WIRE/MAG; 4-8 weeks. | Review/interview if assigned. |
| C | Variety | Entertainment trade; only for major talent/business news, financing/distribution, industry innovation or significant tour announcement. | H: official tips/masthead and current comedy/TV/business reporter. Official page | WIRE/BUS; as real news warrants. | No comp unless assigned. |
| C | Deadline | Entertainment trade; major talent/casting/business/tour news only. | H: official tips/contact; personalised industry pitch. Official page | WIRE/BUS; as news warrants. | No comp unless assigned. |
| C | The Hollywood Reporter | Major entertainment trade; nationally notable talent or industry/business story required. | H: official tips/contact and current beat writer. Official page | WIRE/BUS; as news warrants. | No comp unless assigned. |
| C | TheWrap | Entertainment trade; notable talent, business or trend only. | H: official tips/contact and current writer. Official page | WIRE/BUS; as news warrants. | No comp unless assigned. |
| C | SiriusXM comedy channels | Potential national audio interview or ticket mention when talent has existing SiriusXM relationships or strong current credits. | H: talent publicist/producer relationship is more effective than generic customer contact. Official page | R-COM/WIRE; 6-12 weeks. | Interview/giveaway if invited. |
| C | Travel + Leisure | Cape destination/cultural travel feature only; event must anchor a broader itinerary or trend and be pitched far ahead. | H: current travel editor/writer and official contact. Official page | MAG + TRAVEL; 12-24 weeks. | Feature; no routine review. |
| C | Condé Nast Traveler | National travel long shot; Cape cultural revival/itinerary, exceptional venue or nationally notable talent needed. | H: current editor/writer; premium images and long lead. Official page | MAG + TRAVEL; 12-24 weeks. | Feature only. |
| C | AFAR | Experiential travel feature; authentic local cultural experience and strong photography, well ahead of event. | H: official editorial contact/current writer. Official page | MAG + TRAVEL; 12-24 weeks. | Feature only. |
| C | Atlas Obscura | Only if venue, Cape history or event concept has a genuinely unusual, place-specific story - not a standard listing. | H: official story/place submission route. Official page | MAG + TRAVEL; 8-16 weeks. | Feature only. |
| C | CNN / ABC / CBS / NBC national entertainment desks | One-in-a-million tier for nationally notable talent or a broad, timely culture story. Local affiliates should be exhausted first. | H: official network tips/contact and current entertainment producer. Official page | WIRE/TV; tied to actual national news. | No comp unless assigned. |
| C | National comedy podcasts and creator newsletters | Use performers' existing relationships first. Offer a comic interview and an interesting Cape/circuit question, not a founder sales pitch. | H: show-specific producer/contact; audience and guest fit must be demonstrated. Official page | R-PUB/R-COM + MAG; 4-10 weeks. | Interview; no quid pro quo comp. |
| $ | PR Newswire / Business Wire / GlobeNewswire / ACCESS Newswire | Paid press-release distribution. Useful for searchable announcements and financial/corporate distribution; expensive and not a substitute for local pitching. | H: official sales/platform route; compare geography, syndication, disclosure and reporting. Official page | $DIST after priority earned-media wave. | No comp; paid placement/distribution. |
| $ | EIN Presswire / eReleases / Newswire-style services | Lower-cost paid distribution. Evaluate pickup quality, duplicate-content footprint and whether outlets are genuine editorial placements. | H: official provider; request current distribution list and sample report. Official page | $DIST after personal outreach. | No comp; paid distribution. |
| $ | NENPA press-release service | Most geographically relevant paid backstop: advertised distribution to New England newspapers, including Massachusetts. Confirm current outlet list and service terms. | V: official NENPA page; process after core local editors receive personal pitches. Official page | $DIST; follow stated lead time. | No comp; paid distribution. |

# 11. Launch-day, fact-check and tracking checklists

Directory scale • This edition contains 273 target rows or grouped routes. Some rows represent several titles or stations, so the practical reach is larger. • Use the ranking, profile code and authentic geographic/talent ties to select targets. The goal is not to send the maximum number of emails; it is to leave no plausible route unconsidered.

## The universal first-wave list

| Situation | Send / submit first |
| --- | --- |
| Every Cape event | Cape Cod Times; CapeCod.com/CCB NewsCenter; CAI; Cape Cod Wave; ArtsCapeCod; CapeCod.com calendar; CapeEvents; Cape Cod Chamber; CCB, Coxswain and iHeart Cape radio routes. |
| Venue town | Matching newspaper/weekly; local chamber; community television service; town/local cultural council; municipal calendar if eligible; venue's own newsletter and partner network. |
| Upper Cape | Matching Enterprise title; Falmouth/Sandwich/Mashpee/Bourne community TV and chamber; Wareham Week; WATD; Plymouth Independent when regional relevance exists. |
| Mid Cape | Cape Cod Times; CapeCod.com/CCB; Cape Media Center; Greater Hyannis/Yarmouth/Dennis chambers; ArtsBarnstable; Love Live Local. |
| Lower Cape | Cape Cod Chronicle; Cape Media Center or Lower Cape TV as appropriate; Harwich/Brewster/Chatham/Orleans chambers; Cape Cod Star. |
| Outer Cape | Provincetown Independent; WOMR/WFMR; Lower Cape TV/Provincetown TV; Eastham/Wellfleet/Truro/Provincetown chambers; Provincetown Magazine where fit. |
| Boston feature wave | The Arts Fuse; GBH The Culture Show; WCVB Chronicle; NBC10 The Hub Today; WBUR/GBH News; Boston.com; then Globe, Herald and Boston Magazine when talent/scale supports them. |
| Statewide/paid backstop | MassLive and selected hometown/regional outlets; MBA directory sweep for relevant stations; NENPA paid distribution only after personal Cape and Boston pitches. |
| Review invites | Venue-town arts editor; Cape Cod Times; Provincetown Independent or Chronicle where relevant; Cape Cod Wave; The Arts Fuse; selected Boston/statewide critic with a genuine reason to travel. |

## 48-hour pre-launch freeze

[ ] All talent and venue agreements signed; announcement permissions and billing order in writing.

[ ] Ticket page live, tested on mobile, fees visible, correct time zone/date and no placeholder copy.

[ ] Organisation/legal status wording approved; no unverified 501(c)(3), charity or tax-deduction claims.

[ ] Event fact sheet versioned and approved by venue, talent and organisation owners.

[ ] All links tested in a private browser; media-kit downloads do not require sign-in or permission request.

[ ] Every photograph and clip has written editorial-use rights, captions and credits.

[ ] Talent credits checked against official/current sources; no expired programme or "upcoming" credit presented as current.

[ ] Age/content guidance reviewed against every set; ticket page, listings and email all match.

[ ] Accessibility, parking and press arrival confirmed with venue.

[ ] Founder and backup spokesperson availability locked; written-Q&A route prepared.

[ ] A-priority emails personalised and scheduled in small batches; calendar forms pre-filled.

[ ] Corrections/cancellation protocol and monitoring telephone active.

[ ] Tracking sheet backed up and owned by one person.

## Press release and advisory sign-off checklist

[ ] Headline factual and modest; no unsupported "first", "only", "top" or "historic".

[ ] Opening contains event, date, venue/town and actual significance.

[ ] Cape/non-profit hook appears before background autobiography.

[ ] Exact legal and public organisation name used consistently.

[ ] Venue capacity reflects event configuration.

[ ] Talent names, pronouns, credits and quotation wording approved.

[ ] Ticket price/fees, URL, age, accessibility, doors and start match ticketing system.

[ ] Quotes sound human and add information; no quote makes a claim the fact sheet cannot prove.

[ ] No criticism of existing Cape performers, clubs, venues or promoters.

[ ] Boilerplate is 60-90 words and uses precise legal status.

[ ] Media contact responds quickly; personal information is not exposed publicly.

[ ] Plain-text version tested for copy/paste; PDF/DOCX have no comments, tracked changes or metadata surprises.

[ ] Photo caption/credit immediately available.

[ ] Version/date marked; old drafts removed from shared folders.

## One email - final check

[ ] Correct recipient and outlet; no mail-merge placeholder or wrong town.

[ ] Subject contains a concrete local or programme-specific reason.

[ ] First two sentences are personalised and under 120 words total before the practical facts.

[ ] Ask is explicit: list, preview, interview, review, calendar, PSA, giveaway or correct-desk referral.

[ ] Date, venue/town and media-kit link are visible without scrolling excessively.

[ ] One useful image at most; no unsolicited large ZIP or raw video attachment.

[ ] No demand for coverage and no promise of an exclusive unless agreed.

[ ] Founder's interview preference represented honestly; an available alternative spokesperson named.

[ ] Contact signature complete; sender is monitoring replies and bounces.

[ ] Send/route logged immediately.

## Calendar submission record

| Outlet/calendar | Submitted | Live/approved | URL | Copy length | Image | Correction/re-check |
| --- | --- | --- | --- | --- | --- | --- |
| [name] | [date/time] | [status/date] | [link] | [25/50/100/150] | [filename] | [date/notes] |
| [name] | [date/time] | [status/date] | [link] | [25/50/100/150] | [filename] | [date/notes] |
| [name] | [date/time] | [status/date] | [link] | [25/50/100/150] | [filename] | [date/notes] |
| [name] | [date/time] | [status/date] | [link] | [25/50/100/150] | [filename] | [date/notes] |

## Media relationship and coverage tracker

| Priority | Outlet/contact | Public source | Pitch/ask | Sent | Follow-up | Response/assignment | Comp/attendance | Coverage/correction |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | [outlet / name] | [URL/date] | [profile + angle] | [date] | [date] | [notes] | [seats/status] | [link/notes] |
| A | [outlet / name] | [URL/date] | [profile + angle] | [date] | [date] | [notes] | [seats/status] | [link/notes] |
| B | [outlet / name] | [URL/date] | [profile + angle] | [date] | [date] | [notes] | [seats/status] | [link/notes] |
| C | [outlet / name] | [URL/date] | [profile + angle] | [date] | [date] | [notes] | [seats/status] | [link/notes] |

## Decision rules when time is limited

• Protect quality on A-priority personal pitches before adding more C/D outlets.

• A venue-town weekly with a ready-to-run brief is usually more attainable than a generic national wire pitch.

• Submit calendar forms early; they are often the highest-certainty traditional-media visibility.

• A strong photograph and exact caption often add more publishability than another page of background.

• Use new evidence for follow-up. Repeatedly forwarding the same release can damage the relationship.

• If an outlet has no recent relevant coverage, no current contact and no working submission route, mark it "verify" rather than spending launch morning guessing.

• Do not pay for distribution until earned-media priority contacts have received the news personally.

## Post-event close-out

[ ] Reconcile actual attendance, comps, reviewer attendance and refunds before public claims.

[ ] Deliver approved images/captions to assigned media within the promised window.

[ ] Thank contacts and answer factual questions; do not ask them to change opinion or tone.

[ ] Archive every link/PDF/audio clip and note whether it was earned, calendar, partner, sponsored or paid.

[ ] Record which hook each outlet used; this becomes evidence for the second campaign.

[ ] Update biographies, rights and contacts while the information is fresh.

[ ] Publish a concise results/next-step page and keep the media kit live.

[ ] Review artist and audience feedback against the organisation's two promises: artist respect and audience quality.

# 12. Source, verification and maintenance notes

Media contacts, ownership, programmes, calendars and fees change. The links below were selected from official outlet/service pages or authoritative member directories and checked during preparation on 12 July 2026. Re-check each route immediately before launch.

| Source | What it verifies | Official route |
| --- | --- | --- |
| Cape Cod Times | Official support/contact and public newsroom route. | Open official page |
| Cape Cod Chronicle | Official contact page. | Open official page |
| Provincetown Independent | Official contact page; arts notice guidance included on site. | Open official page |
| CapeNews / Enterprise papers | Official group contact. | Open official page |
| CAI | Official contact and public-service information. | Open official page |
| CapeCod.com / Cape Cod Broadcasting | Official news submission, contact and events routes. | Open official page |
| Coxswain Media / Cape Cod Radio | Official station/contact/calendar routes. | Open official page |
| ArtsCapeCod | Official event-submission route. | Open official page |
| Cape Cod Chamber | Official regional events/visitor route. | Open official page |
| Community television services | Official station/service sites listed in the directory; town eligibility varies. | Open official page |
| WBUR | Official contact and public newsroom email. | Open official page |
| GBH | Official news/programme contact routes. | Open official page |
| WCVB | Official contact page with programme and community emails. | Open official page |
| CBS News Boston / WBZ-TV | Official contact and news-tip route. | Open official page |
| Massachusetts Broadcasters Association | Current member directory for station-by-station verification. | Open official page |
| NENPA | Official New England press-release service. Price, outlet count and processing time must be re-confirmed at purchase. | Open official page |
| AP | Official contact page; generic local event releases require a genuine wider news peg. | Open official page |
| Reuters | Official confidential tips route; not a routine release inbox. | Open official page |
| PBS NewsHour | Official contact route. | Open official page |
| IRS | Official guidance on charitable contributions and benefits received. | Open official page |
| Massachusetts Attorney General / charities | Official Massachusetts charitable-organisation and fundraising guidance. | Open official page |
| Mass Cultural Council | Official local cultural council directory. | Open official page |
| Press Forward Massachusetts | Current local-news ecosystem and chapter resource. | Open official page |

## Current-route notes worth retaining

• The Provincetown Independent's public guidance asks for arts notices at least two weeks before publication; earlier is still preferable for a feature or review.

• CAI publishes a general contact and a public-service/community route; use the PSA/calendar process separately from an editorial programme pitch.

• WCVB publishes programme-specific contacts including Chronicle, 5 For Good, Made in Mass and CityLine; each requires a distinct angle.

• WBUR and GBH publish general newsroom contacts, but a named current reporter or programme producer remains more effective than a generic release.

• The NENPA press-release service publicly advertises New England newspaper distribution and a processing window; price, total outlets and deadlines should be confirmed on the purchase date.

• Cape Cod Daily News is a paid press-release service; report it as paid placement/distribution, not independent editorial pickup.

• Cape Wide News explicitly prioritises breaking/public-safety information; routine entertainment releases should not be forced into that route.

• The Massachusetts Broadcasters Association directory is the best maintenance backstop for current station names, ownership and official websites.

## Quarterly maintenance routine

[ ] Re-open all A/B links; remove redirects, inactive titles and dead emails.

[ ] Search each priority outlet for the last 90 days of comedy, Cape arts, tourism and non-profit coverage; record current writers/producers.

[ ] Check station ownership, programme names, formats and community-calendar/PSA policies through the MBA directory and official sites.

[ ] Refresh chamber, tourism and calendar eligibility, fees and image specifications.

[ ] Update national comedy writers only when the line-up is known; talent news determines which trade outlets are rational.

[ ] Preserve an opt-out/suppression list and contact-source date.

[ ] Version the directory: YYYY-MM-DD, editor, change and source.

Final strategic reminder • The release should not ask editors to believe that Cape Cod has lost comedy. It should show, with optimism and evidence, that The 1140-A Company is adding an ambitious, artist-respectful, audience-centred institution to the Cape's cultural life. • The most effective package gives an outlet three things at once: a story worth telling, facts safe to publish, and assets that remove work.